## Slide 1: make a selection
Individual use
Instructor led
Please use this training in SLIDE SHOW mode

## Slide 2: Maintenance Activity Training (MAT) Pipe Replacement
Welcome
to the PennDOT
Pipe Replacement
Maintenance Activity Code:
711-7324-01
Revised December, 2012
introduction
Notes: Welcome to the PennDOT training for pipe replacement.
This training is intended for PennDOT department force personnel responsible for planning scheduling and completing this activity.

## Slide 3: Welcome to Pipe Replacement
This training is intended for PennDOT personnel responsible for
Planning, Scheduling, and Conducting Pipe Replacement Activities.
Copyright © 2011 by the Commonwealth of Pennsylvania. All rights reserved. No part of this training may be reproduced, stored in a retrieval system, or transmitted in any form or by any means electronic, mechanical, photocopying, recording or otherwise without prior written permission by PennDOT.
This training course was developed in partnership with the Pennsylvania Department of Transportation’s Business Leadership and Administrative Services Office and the Bureau of Maintenance and Operations, and the Indiana University of Pennsylvania. It is offered as part of the Pennsylvania Department of Transportation’s Highway Administration Comprehensive Training Plan exclusively through the Technical Training and Development Section.
introduction

## Slide 4: How to use this training
This training is non-linear, which allows for:
  Flexibility to select modules based on classification of the participant
  Can be adjusted for time allotments
  Can be used at remote training sites
introduction

## Slide 5: How to use this training
Managers participating in this training should review at a minimum the following modules:
  Project Planning
  Project Preparation
  Concurrent Activities
  Scheduling
  Safety
  Quality Assurance
  Environmental Concerns
  Risk Management
  Follow-up Activities
  Preventive Maintenance
introduction

## Slide 6: How to use this training
Foremen participating in this training should review all modules in this training.
Crew members participating in this training should review at a minimum the following modules:
  Safety
  Work Zone Traffic Control
  Quality Assurance
  Environmental Concerns
  Risk Management
  Operational Sequence
introduction

## Slide 7: How to use this training
Navigate from slide to slide using the navigation arrows in the lower right hand corner of the slide.
Return to the module selector slide at any time by clicking on the training logo in the lower left-hand corner.
Click any text in this highlighted field to view the corresponding text or graphics
introduction
Notes: To navigate this training you can use the up and down arrow keys on your keyboard or use the arrows in the lower right hand corner of the slide.
When you see a highlighted field on a slide click on the highlight to view additional information or graphics. Click on the highlight a second time to restore the slide.

## Slide 8: How to use this training
Navigate from slide to slide using the navigation arrows in the lower right hand corner of the slide.
Go back to the module selector slide at anytime by pressing the training logo in the lower left-hand corner
Click any text in this highlighted field to view the corresponding text or graphics
This is where additional information can be found.
Return to selector page
introduction
Notes: To navigate this training you can use the up and down arrow keys on your keyboard or use the arrows in the lower right hand corner of the slide.
When you see a highlighted field on a slide click on the highlight to view additional information or graphics. Click on the highlight a second time to restore the slide.

## Slide 9
At the start of each module, you will see a list of learning objectives.
These are the primary objectives of the module and where you should focus your attention.
introduction

## Slide 10
Within the module, the key topics from the learning objectives will be indicated by this KEY TOPICS tag.
introduction

## Slide 11
Each learning module will end with a summary of the learning objectives and key topics that were addressed in the module.
introduction

## Slide 12: The Director’s Safety Message Take Safety Seriously!
While mission is the central focus of our operations, safety is paramount. Ignoring it results in increased costs and lost production. More importantly it can result in lost lives or disabling injuries for co-workers and/or customers with irreversible impacts on their lives and families.
Reducing or eliminating risks which create unsafe conditions is an essential part of any job. Getting the job done is only half of it. Getting the job done right ensures the safest conditions for our fellow employees and our customers who entrust us with their lives and livelihood with each journey on our roads.
This training addresses essential maintenance activities which you will encounter in your job as well as the risks associated with them. It emphasizes the safe way to perform each task to reduce or eliminate these risks.
For your safety and those whose lives are affected by your actions, don’t take risks. Take Safety seriously!
introduction
Notes: Each training module has activity specific safety concerns. For the safety of the crew members and motoring Public it is important that every crew member associated with the activity be familiarized with the safety concerns.

## Slide 13: Safety concerns for this learning module
Like many activities performed by PennDOT Maintenance Personnel, these operations can be extremely dangerous.
Please review and pay close attention to the Safety and Work Zone Traffic Control Modules of this training.
Never compromise the safety of the crew or the motoring Public while performing this or any other maintenance activity!
introduction

## Slide 14: Pipe Replacement (711-7324-01)
This activity includes all tasks and related actions associated with the installation or replacement of pipes and culverts under 36 inches in diameter
such as:
introduction

## Slide 15: Sawing or cutting the pavement
introduction

## Slide 16: Excavating the trench
introduction

## Slide 17: Placing the bedding material
introduction

## Slide 18: Installing the pipe
introduction

## Slide 19: Backfilling
introduction

## Slide 20: Trench compaction
introduction

## Slide 21
The following slide allows you to select the specific training module you would like to view.
To return to this module selector, simply click the module icon located in the lower left-hand corner of every slide.
introduction

## Slide 23: Planning
Planning

## Slide 24
Define Maintenance Planning Strategies
Describe proactive maintenance strategies
Compare and contrast the different maintenance planning strategies
Planning

## Slide 25: Maintenance Planning Strategies
Maintenance Strategies are the practices used to provide a deliberate and coherent 'road map' for County Management to follow in order to achieve the following goals:
  Reduce breakdowns, maximize the life of the roadways and bridges and improve productivity
  Maximize limited resources through controlled spending and adherence to budgets
  Ensure compliance with established Department goals and objectives
  Adherence to all applicable policies and regulations
Planning

## Slide 26: Reactive vs. Proactive Strategies
Demand Maintenance (reactive)
Preventive Maintenance (proactive)
    Preventive Maintenance
    Cyclical Preventive Maintenance
    Surface Improvement Preparatory
Planning

## Slide 27: Demand Maintenance Strategies
  Simply put, demand or reactive maintenance is any activity conducted in response to a maintenance condition or deficiency that demands a maintenance activity be performed to correct it.
Planning

## Slide 28: Examples of Demand Maintenance for Pipe Replacement
The pipe has separated or collapsed
Planning

## Slide 29: Examples of Demand Maintenance for Pipe Replacement
The pipe has rusted out
Planning

## Slide 30: Examples of Demand Maintenance for Pipe Replacement
Maybe a little of both?
Planning

## Slide 31: Preventative Maintenance Strategies
  Preventive Maintenance
  Schedule of planned maintenance actions aimed at the prevention of breakdowns and failures
  Primary goals:
    prevent the failure of roadways and bridges before it occurs
    extend the serviceable life of the roadways and bridges
  Strategies include:
    Cyclical Maintenance
    Preventative Maintenance
    Surface Improvement Preparatory Maintenance
Planning

## Slide 32: Cyclical Strategies
  Cyclical preventive maintenance is preventive maintenance performed on a pre-established interval
  All cyclical maintenance is preventative but not all preventative maintenance is cyclical.
Planning

## Slide 33: Cyclical Strategies
  Cyclical preventive maintenance is preventive maintenance performed on a pre-established interval
  All cyclical maintenance is preventative but not all preventative maintenance is cyclical.
Cutting shoulders is a preventive maintenance activity, cutting shoulders at pre-determined intervals such as every three to five years is cyclical preventive maintenance.
Planning

## Slide 34: Surface Improvement Strategies
  Surface improvement preparatory activities are activities that should be completed prior to performing a surface improvement project.
  Completion of these activities helps maximize the useful lifespan of the completed surface improvement project.
Planning

## Slide 35: Surface Improvement Strategies
  Surface improvement preparatory activities are activities that should be completed prior to performing a surface improvement project.
  Completion of these activities helps maximize the useful lifespan of the completed surface improvement project.
Preparatory activities include; pipe replacement, widening, base repair, crack sealing, pothole repair, shoulder cutting and brushing.
Planning

## Slide 36: Preventive Maintenance for Pipe Replacement
Preventive and Cyclical Preventive Maintenance
are not the most effective proactive strategies for pipe replacement.
However,
Pipe replacement in preparation for surface improvement activities is not only more effective, it is critical to the longevity of the completed surface improvement project.
Planning

## Slide 37: Example of Preventive Maintenance for Pipe Replacement
Strategy:
Identify and replace any pipes that could fail before the new surface improvement project reaches the end of its predicted lifecycle.
Planning

## Slide 38: Maintenance Planning Strategies Compared
Qualities | Demand | Preventative | Preparatory
Reactive |  |  | 
Inefficient |  |  | 
Hampers immediate and long-range planning efforts |  |  | 
Proactive |  |  | 
Efficient |  |  | 
Supports immediate and long-range planning efforts |  |  | 
Helps extend useful life of surface improvement project |  |  | 
Planning

## Slide 39: Weekly Planning Meeting
All of the long-range planning comes together at the Weekly Planning Meeting
Planning

## Slide 40: Weekly Planning Meeting
Planning and preparation for a quality pipe replacement operation begins long before the Weekly Planning Meeting.
This is true for all maintenance related operations.
Planning

## Slide 41: Issues Discussed at the Weekly Planning Meeting
  What you plan to do?
  Where you plan to do it?
  How much will be completed?
  Work Zone Traffic Control required
  Environmental concerns
    Permits
    Erosion and sedimentation controls
Planning

## Slide 42: Issues Discussed at the Weekly Planning Meeting
  (continued)
  Customer concerns
  Required resources such as:
    Personnel
    Equipment
    Materials
Planning

## Slide 43: Attributes of a Well-Planned Activity
Cost effective
Includes planned events, such as widening or surface improvements
Helps extend useful life of roadway
Minimizes tort liability
Planning

## Slide 44: Attributes of a Well-Planned Activity
Reflects best use of resources – manpower and equipment
Attracts positive PR
Maximizes life of the asset (pipe)
Planning

## Slide 45: Attributes of a Well-Planned Activity
Enables competitive pricing and advance stocking for necessary materials
Planning

## Slide 46: Attributes of a Well-Planned Activity
Enables improved coordination of other related activities.
Planning

## Slide 47: Attributes of a Well-Planned Activity
Enables improved coordination of other related activities.
Examples of related activities for pipe replacement are; headwalls, cleaning inlet ditches and tail ditches, trench restoration, installation of delineators and resetting guiderail.
Planning

## Slide 48: Attributes of a Well-Planned Activity
Allows time to obtain necessary permits
Minimizes environmental impacts
Planning

## Slide 49: Attributes of a Well-Planned Activity
Addresses safety issues
811
Know what's below,
Call before you dig.
Planning

## Slide 50: Agility
Consider using Agility Agreements as part of your work planning to improve operational efficiency and enhance collaboration within your county.
Click here to learn more about Agility
Planning

## Slide 51
Define Maintenance Planning Strategies
Identify reactive and proactive maintenance strategies
Compare and contrast the different maintenance planning strategies
Planning

## Slide 52
Define Maintenance Planning Strategies
Identify reactive and proactive maintenance strategies
Compare and contrast the different maintenance planning strategies
Reactive or Demand Maintenance is performed to address an existing condition. Proactive or preventive Maintenance is performed to prevent breakdowns and failures.
Planning

## Slide 53
Define Maintenance Planning Strategies
Identify reactive and proactive maintenance strategies
Compare and contrast the different maintenance planning strategies
Demand Maintenance
Preventative Maintenance
Cyclical Preventative Maintenance
Surface Improvement Preparation
Planning

## Slide 54
Define Maintenance Planning Strategies
Identify reactive and proactive maintenance strategies
Compare and contrast the different maintenance planning strategies
Pro-active strategies are more effective, more efficient and support the organization’s intermediate and long-range planning efforts.
Planning

## Slide 56: What is Agility?
Agility

## Slide 57: Agility is …
Agility is a “way of doing business”
  Allows PennDOT and eligible partners to exchange services with each other
  Develops relationships between PennDOT and partners
  Service exchanges are reasonably equal in value
City of Hermitage is providing winter services to PennDOT as an Agility exchange
Agility
Notes: Alternative way of doing business that:
Saves money and improves cash flow
Improves service quality
Improves safety
Stretches available resources
Focuses on collective organizational strengths
Develops and strengthens relationships

## Slide 58: Agility at PennDOT
New focus on Modernization:
Regionalizing Services
  Sharing of equipment
  Training Sessions
Increasing inter-agency cooperation
  Pennsylvania Turnpike Commission (PTC)
  Pennsylvania Human Relations Commission (PHRC)
  Department of Conservation & Natural Resources (DCNR)
Agility strengthens relationship between PennDOT and DCNR
Agility

## Slide 59: Agility Examples …
What are some potential Agility exchange opportunities for your organization?
Sharing
Storage
Maintenance
Training
Emergency Response
Safety
Training
Technology
Facilities/
Equipment
Services
Plowing
Line Painting
Seal Coating
Mowing
Mapping
Roadway Inventories
Maintenance
Graphic Services
Communications
Information sharing
Back-up crews
Debris removal
Low-cost safety improvements
Brush/tree trimming
Sign maintenance
Training
Technical
Management
Software
First Aid/CPR
CDL
Agility

## Slide 60: Agility Examples
Note to self … change following slides to table
Category | Agility Partner | Partner Activity | PennDOT Exchange
Maintenance | Municipality | Mowing | Sign & post installation
 | Municipality | Winter maintenance | Reface bridge abutments
 | DCNR | Boats for bridge inspections | Dust control
Bridges | Fire Department | Bridge flushing | Parking lot paving
 | State University | Training Meeting facilities | Installation of Timber Bridge Deck
Safety | Municipality | Ongoing removal of tree limbs | Installation of rumble strips
Agility

## Slide 61
To get started….
CONTACT:
  Agility Division at 717-705-1333
  District Agility Coordinator
  County Agility Coordinator
Agility partnership with Allegheny College
Agility
Next
Notes: This is great cooperation! Students from Allegheny College in Pennsylvania team up with PennDOT to produce lovely metal flowers from old road signs.

## Slide 62: Project preparation
Project preparation

## Slide 63
Identify preparatory activities associated with a typical pipe installation project.
Identify the time frames associated with each of the activities.
Identify and describe the supporting documents typically needed for a pipe installation project.
Project preparation

## Slide 64: Project Preparation
Project preparation ensures activities are identified and completed in the correct order…
Project preparation

## Slide 65: Why preparation is important
Improves activity efficiency:
  Lowers cost
  Improves productivity
Improves activity effectiveness:
  Correct number of personnel are trained and available
  Correct types and amounts of equipment are available
  Correct types and amounts of materials stocked and ready for use
Project preparation

## Slide 66: Why preparation is important
Minimizes Environmental Impacts:
  Hydraulic Studies are completed
  Permits are obtained
  Erosion & Sedimentation controls are available
Improves Safety:
  Work Zone Traffic Control plans are established
  Identifies and addresses jobsite safety concerns
Project preparation

## Slide 67: Project Preparation Time Frames
Long-range Plan
1 Year + prior to the start of the activity
Intermediate-range Plan
Several weeks to 1 year
Short-term Plan
1 day to several weeks
Project preparation

## Slide 68: Long-range Preparatory Activities
Authorization to Enter form M-666
Conduct site visit to determine:
    Existing condition
    Appropriate response to condition
      Clean pipe
      Replace pipe
    Identify potential environmental impacts
      Proximity to streams
      Historical values
    Identify the limits of work
      Length of pipe
      Inlets or headwalls
      Type pipe
            Corrugated plastic
            Reinforced concrete
            Corrugated metal
            Round or elliptical
Project preparation

## Slide 69
Project preparation

## Slide 70: Long-range Preparatory Activities
Prepare hydraulic studies if required
  If changing pipe size or current pipe appears to be inadequate, request a hydraulic study through the Engineering District
Secure environmental permits as required
  When environmental permits are required, work with the Engineering District
Identify stakeholders affected by the activity
  Adjacent property owners
  Businesses
  Municipalities
  Department of Environmental Protection (DEP)
  U.S. Army Corps of Engineers
  Soil Conservation Offices
Project preparation

## Slide 71: Intermediate-range Preparatory Activities
Determine and procure materials for activity
  Pipe
  Aggregate
  E&S controls
  Trench restoration material
Determine specialized equipment availability
  Excavator
  Compactors
Project preparation

## Slide 72: Intermediate-range Preparatory Activities
Determine personnel skills needed, ensure certified TEO’s are available for specialized equipment
  Excavator operator
Provide training to crew to include
  Pipe QA
  Trench restoration
Project preparation

## Slide 73: Intermediate-range Preparatory Activities
    Review site to determine safety needs
      Work zone traffic control
      Worksite safety issues
      Trenching/Shoring requirements
      Backing Equipment
    Identify waste dump sites and complete “Authorization to Enter” form (Form M666)
    Notify select customer
      Schools
      Emergency services providers
      Businesses
      Municipalities
      Other community leaders
Project preparation

## Slide 74: Short-term Preparatory Activities
Schedule activity (one week prior to start of the activity)
  In accordance with Publication 113 Assembly Requirements
Identify and schedule concurrent activities (one week prior to start of the activity)
  In accordance with Publication 113 Assembly Requirements
    Headwalls/inlets
    Clean tail ditches
    Reset affected guiderail and signs
    Install delineators
    Brushing
    Litter pickup
Project preparation

## Slide 75: Short-term Preparatory Activities
  3. Review relevant Publications (one to two weeks prior to start of the activity)
      Pub. 113
      Pub. 23
      Pub. 213
      Pub. 464
Project preparation

## Slide 76: Short-term Preparatory Activities
  3. Review relevant Publications (one to two weeks prior to start of the activity)
      Pub. 113
      Pub. 23
      Pub. 213
      Pub. 464
Project preparation

## Slide 77: Short-term Preparatory Activities
  3. Review relevant Publications (one to two weeks prior to start of the activity)
      Pub. 113
      Pub. 23
      Pub. 213
      Pub. 464
Project preparation

## Slide 78: Short-term Preparatory Activities
  3. Review relevant Publications (one to two weeks prior to start of the activity)
      Pub. 113
      Pub. 23
      Pub. 213
      Pub. 464
Project preparation

## Slide 79: Short-term Preparatory Activities
  3. Review relevant Publications (one to two weeks prior to start of the activity)
      Pub 113
      Pub 23
      Pub 213
      Pub 464
Jeremy, Pub 464 cover here
Project preparation

## Slide 80: Short-term Preparatory Activities
Initiate PA One Call (up to ten working days and no less than three working days prior to the start of the activity)
Cut the roadway and establish grade (at least one day prior to the start of the activity)
Project preparation

## Slide 81: Short-term Preparatory Activities
Verify material availability (one week prior to the start of the activity)
  Pipe
  Pipe bands
  Aggregates
  Trench restoration material
Verify equipment availability (one week prior to the start of the activity)
  Excavator
  Compactors
  Trucks
  Loader at stockpile
Check leave schedule for personnel availability (one week prior to the start of the activity)
Project preparation

## Slide 82: Short-term Preparatory Activities
Communicate pending activities
  Inform motoring Public
  Notify affected property owners
  Notify businesses
  Consider concurrent activities and community events
Vary communication methods
  Variable message boards
  Weekly news release
  Traffax (radio and television traffic updates)
Project preparation

## Slide 83
Identify preparatory activities and time frames associated with a typical pipe installation project Long-range
Identify the time frames associated with each of the activities
Identify and describe the supporting documents typically needed for a pipe installation project
Project preparation

## Slide 84
Identify preparatory activities and time frames associated with a typical pipe installation project Long-range
Identify the time frames associated with each of the activities
Identify and describe the supporting documents typically needed for a pipe installation project
Conduct site to determine; existing conditions, potential environmental impacts and the limits of work.
Prepare hydraulic studies, secure environmental permits and identify stakeholders affected by the activity.
Project preparation

## Slide 85
Identify preparatory activities and time frames associated with a typical pipe installation project Long-range
Identify the time frames associated with each of the activities
Identify and describe the supporting documents typically needed for a pipe installation project
Long-range - Determine and procure materials, determine specialized equipment availability, determine personnel skills needed, ensure certified TEO’s are available and provide training to the crew.
Intermediate-range - Review worksite to determine safety needs, identify waste dump sites and prepare documentation and notify adjacent property owners, EMS and schools.
Short-term - Review relevant PennDOT Publications, initiate PA 1 call and schedule the work activity along with concurrent activities that are to be completed.
Establish grade and cut roadway.
Project preparation

## Slide 86
Identify preparatory activities and time frames associated with a typical pipe installation project Long-range
Identify the time frames associated with each of the activities
Identify and describe the supporting documents typically needed for a pipe installation project
Publication 113, Highway Foreman Manual,
Publication 23, PennDOT Maintenance Manual,
Publication 213, Temporary Traffic Control Guidelines, and
Publication 464, Erosion and Sedimentation Control Best Practices.
Project preparation

## Slide 88: Concurrent maintenance activities
Concurrent Activities

## Slide 89
Understand why we plan for and conduct concurrent maintenance activities
Identify concurrent maintenance activities associated with a pipe replacement project
Concurrent Activities

## Slide 90: Planning and Conducting Concurrent Maintenance Activities
Not performing concurrent or secondary maintenance activities in conjunction with the primary activity is like going to the grocery store and not purchasing everything on your list. You will have to go back, it will cost more, and there may be serious consequences.
Concurrent Activities

## Slide 91: Planning for concurrent maintenance activities is important
Benefits - Operational Efficiency:
    Performing multiple activities reduces mobilization and travel costs.
    Some activities can be performed during slow periods of the primary activity which will help keep crew members productive.
    More work is completed during an average crew day.
Consequences - Tort Liability:
    Temporary trench restoration to minimize loose aggregate hazards
    Delineator installation identifies ditch or headwall
    Replacement of signs and guiderail to inform and protect the motoring Public
Concurrent Activities

## Slide 92: Concurrent activities associated with a pipe replacement project
Activities that can/should be performed and charged in conjunction with a typical pipe replacement activity:
    Construction of inlets and end walls
    Inlet and tail ditch cleaning, greater than 15 feet from the pipe
    Rock filters and other erosion and sedimentation controls
    Delineator installation
    Sign and guiderail reinstallation
Concurrent Activities

## Slide 93
Installing inlets
Erosion Control
Concurrent Activities

## Slide 94: Concurrent activities associated with pipe replacement
Additional activities that can and should be performed and charged that are not usually performed in conjunction with a typical pipe replacement activity:
    Brush cutting
    Litter pickup
Concurrent Activities

## Slide 95
Understand why we plan for and conduct concurrent maintenance activities
Identify concurrent maintenance activities associated with a pipe replacement project
Concurrent Activities

## Slide 96
Understand why we plan for and conduct concurrent maintenance activities
Identify concurrent maintenance activities associated with a pipe replacement project
Improves operational efficiency and helps reduce tort liability.
Concurrent Activities

## Slide 97
Understand why we plan for and conduct concurrent maintenance activities
Identify concurrent maintenance activities associated with a pipe replacement project
Construction of inlets and end walls
Inlet and tail ditch cleaning, greater than 15 feet from the pipe
Rock filters and other erosion and sedimentation controls
Delineator installation
Sign and guiderail reinstallation
Brush cutting
Litter pickup
Concurrent Activities

## Slide 99: Project scheduling
Project Scheduling

## Slide 100
Understand how proper crew size is determined.
Realize the affects of correct and incorrect crew sizing on budget and plan.
Project Scheduling

## Slide 101: Scheduling a Pipe Replacement Crew
Not every pipe replacement operation is “textbook standard”
Schedule and utilize the right personnel and equipment for the conditions encountered
Project Scheduling

## Slide 102: “Right Sizing” the Crew
Too many
Wasteful
Not enough
    Unsafe, Inefficient
Right size
    Number of personnel & equipment reflects conditions/needs
Project Scheduling

## Slide 103
Guidelines for proper crew size can be found in Publication 113
Project Scheduling

## Slide 104
Guidelines for proper crew size can be found in Publication 113
Project Scheduling

## Slide 105
Standard Crew Size
Standard Equipment List
Pub 113
Assembly Requirements for
Pipe Replacement
Production Standards
Project Scheduling

## Slide 106
Standard Crew Size
Standard Equipment List
Pub 113
Assembly Requirements for
Pipe Replacement
Production Standards
Project Scheduling

## Slide 107
Standard Crew Size
Standard Equipment List
Pub 113
Assembly Requirements for
Pipe Replacement
Production Standards
Project Scheduling

## Slide 108
Standard Crew Size
Standard Equipment List
Pub 113
Assembly Requirements for
Pipe Replacement
Production Standards
Project Scheduling

## Slide 109: Affect on Budget & Plan Crew too Large
Drives up costs
    Adding more personnel or equipment than required inflates project cost
Drives down productivity
Prevents other needed work from being completed
  Every hour needlessly spent on a project prevents another project from being completed
Project Scheduling

## Slide 110: Affect on Budget & Plan Crew too Small
Inefficient
    Can result in overtime costs
  May compromise quality
    Time consuming portions of the operation such as proper backfilling and compaction tend to be sacrificed
  Unsafe
    Never sacrifice safety due to short crew staffing
Project Scheduling

## Slide 111: Affect on Budget & Plan Right Size
Personnel and equipment types and amounts are based on Publication 113, “Assembly Requirements for Pipe Replacement” with adjustments for field conditions
When more personnel are assigned than required, additional work activities should be identified and assigned
When fewer personnel are assigned than required:
    Request additional resources
    Maintain quality standards
    Sacrifice productivity when necessary
  Never compromise the safety of the crew or motoring Public
Project Scheduling

## Slide 112
Understand how a proper crew size is determined
Realize the affects of correct and incorrect crew sizing on budget and plan
Project Scheduling

## Slide 113
Understand how a proper crew size is determined
Realize the affects of correct and incorrect crew sizing on budget and plan
Proper crew size guidelines for every maintenance activity can be found in Publication 113. Field conditions may require adjustments to the recommended guidelines.
Project Scheduling

## Slide 114
Understand how a proper crew size is determined
Realize the affects of correct and incorrect crew sizing on budget and plan
Overstaffing a crew drives costs up and productivity down. Understaffing a crew can be inefficient may affect quality and could compromise the safety of the crew and the motoring Public.
Project Scheduling

## Slide 116: safety
Safety

## Slide 117
Identify and refer to the source documents for safety related information
Identify the safety concerns relative to a pipe replacement operation
Safety

## Slide 118: Source Documents
Publication 445, “Safety Policy Manual”
    Daily Safety Talks
    Proper attire
    Personal Protective Equipment (PPE)
    Injury management procedures
Safety

## Slide 119: Source Documents
Publication 445, “Safety Policy Manual”
    Daily Safety Talks
    Proper attire
    Personal Protective Equipment (PPE)
    Injury management procedures
Safety

## Slide 120: Source Documents
Publication 113, Highway Foreman Manual
    Buried/underground hazards
Safety

## Slide 121: Source Documents
Publication 113, Highway Foreman Manual
      PA One-Call (up to ten working days before the operation begins, no less than three working days)
811
Know what's below,
Call before you dig.
Safety

## Slide 122: Source Documents
Publication 113, Highway Foreman Manual
      PA One-Call (up to ten working days before the operation begins, no less than three working days)
811
Know what's below,
Call before you dig.
IT IS A LAW. Failure to comply not only endangers the crew, it places you and the Department at risk for civil and criminal prosecution.
Safety

## Slide 123
Disruption of any one of these services can adversely impact day to day life, and unexpectedly finding any one of these during an excavation operation can be very costly, both in terms of human life and money.
Safety

## Slide 124: Source Documents
Publication 113, Highway Foreman Manual
    Overhead Hazards
Safety

## Slide 125: Source Documents
Publication 113, Highway Foreman Manual
    Trench Safety (trenches greater than 5 feet deep require wider cuts or shoring)
Safety

## Slide 126: Source Documents
Publication 113, Highway Foreman Manual
    Material handling, care should be taken to not maneuver pipe over the heads of the personnel
Safety

## Slide 127: Source Documents
Publication 113, Highway Foreman Manual
    Encroaching into the travel lanes
Safety

## Slide 128: Source Documents
Publication 213, Temporary Traffic Control Guidelines, Pennsylvania Typical Applications (PATA) 10a and 11d
  PATA 10a (most commonly used)
  PATA 11d (recommended when possible)
Safety

## Slide 129: Source Documents
Publication 213, Temporary Traffic Control Guidelines, Pennsylvania Typical Applications (PATA) 10a and 11d
  PATA 10a (most commonly used)
  PATA 11d (recommended when possible)
Safety

## Slide 130
PATA 10a
Most Commonly Used Traffic Control PATA
Before selecting and applying this or any other traffic control figure, reference and review all of the notes on the related page(s) of the current traffic control Publication.
Pipe Replacement
Work Zone Traffic Control
Safety

## Slide 131
PATA 10a
Most Commonly Used Traffic Control PATA
Before selecting and applying this or any other traffic control figure, reference and review all of the notes on the related page(s) of the current traffic control Publication.
Pipe Replacement
Work Zone Traffic Control
Safety

## Slide 132
.
Work Zone Traffic Control
Pipe Replacement
PATA 11d.
This is by far the preferred environment in which to perform roadway maintenance ….one where there is no traffic. This short term daylight detour affords maintenance crews an opportunity to detour traffic around their operation, reducing manpower requirements for flagging, and increasing both efficiency and quality. Remember to review all notes when using this PATA.
Safety

## Slide 133
.
Work Zone Traffic Control
Pipe Replacement
PATA 11d.
This is by far the preferred environment in which to perform roadway maintenance ….one where there is no traffic. This short term daylight detour affords maintenance crews an opportunity to detour traffic around their operation, reducing manpower requirements for flagging, and increasing both efficiency and quality. Remember to review all notes when using this PATA.
Safety

## Slide 134
Work Zone Traffic Control
Pipe Replacement
Many crews utilize high strength steel plates to accommodate thru traffic under PATA 10a. Extreme caution must be exercised during placement and removal.
Safety

## Slide 135
Work Zone Traffic Control
Pipe Replacement
PATA 10a.
Using steel plates to accommodate thru traffic
Safety

## Slide 136
More detailed training on work zone traffic control can be found in the
Work Zone Traffic Control
Module
of this program
Safety

## Slide 137
Identify and refer to the source documents for safety related information
Identify the safety concerns relative to a pipe replacement operation
Safety

## Slide 138
Identify and refer to the source documents for safety related information
Identify the safety concerns relative to a pipe replacement operation
Safety related source documents include; Publication 113 (Highway Foreman Manual), Publication 445 (Safety Policy Manual) and Publication 213 (Temporary Traffic Control Guidelines)
Safety

## Slide 139
Identify and refer to the source documents for safety related information
Identify the safety concerns relative to a pipe replacement operation
Pipe replacement safety concerns include; buried/underground hazards, overhead hazards, trench safety and work zone traffic control.
Safety

## Slide 141: Work zone traffic Control (WZTC)
WZTC

## Slide 142
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety.
Reference specific information to improve safety in Department work zones.
Be familiar with Publication 213, PENNSYLANIA TYPICAL APPLICATIONS (PATA) and associated common problem areas.
Identify the primary topic areas and guidelines in Publication 213.
WZTC

## Slide 143: Why Is WZTC Important?
We have the responsibility to protect
  our work force
  the motoring Public.
It can minimize tort liability
It is the law.
WZTC

## Slide 144: Manual on Uniform Traffic Control (MUTCD)
Defines “minimum” traffic control requirements under the Law
Directs the installation and maintenance of traffic control devices used by road managers nationwide
Includes all Public streets, highways, bikeways, and private roads open to Public traffic
Published by the Federal Highway Administration (FHWA)
  23 Code of Federal Regulations (CFR), Part 655, Subpart F.
State Supplement
  Chapter 212 and Chapter 213, Title 67, Pennsylvania Code
  Pub 236, “Official Traffic Control Devices”
WZTC

## Slide 145: WZTC: Primary Components
WZTC
Advanced warning of work area
Specific directions and instructions
Delineation of the work area

## Slide 146: WZTC: Primary Components
Advanced Warning of Work Area signing includes:
  “Road Work Ahead”
  “One Lane Road Ahead”
  “Flagger Ahead”
  “Road Closed Ahead”
  “Be Prepared to Stop”
WZTC

## Slide 147: WZTC: Primary Components
Specific directions and instructions for:
  Flaggers
  Proper Placement of Flagger
  Tapers
  “Reduced Speed Limit” signing
  Arrow boards
  Pilot vehicles
WZTC

## Slide 148: WZTC: Primary Components
Delineation of the work area
  Vertical Panels
  Cones
  Barrels
  Barriers
WZTC

## Slide 149: Work Zone Traffic Control
Work Zone Traffic Control is required on highway construction, maintenance operations and utility work or incident management, either on a highway or so close to a highway that workers, equipment or materials encroach on the highway.
Compliance with this subchapter does not relieve the contractor or others of their general responsibility for the protection of the Public and the employees in work zones.
Minimum requirements for the development and administration of traffic control plans and the application, maintenance and disposition of traffic control devices.
WZTC

## Slide 150: WZTC: Pipe Replacement
PATAs most commonly used
Pub. 213 PATA 10a. – Stationary, Short Term Operation, Two-Lane, Two-Way Roadway – Flagging
Pub. 213 PATA 11d. – Stationary, Short Term Operation, Two-Lane, Two-Way Roadway – Road Closure
WZTC

## Slide 151: WZTC: Routine Maintenance Focus Areas
Commonly used PATAs and Related Maintenance Activities
Pub. 213 PATA 10a. – Stationary, Short-Term Operation, Two-Lane, Two-Way Roadway - Flagging
    Base Repair
    Pipe Replacement
    Standard Pothole Patching
    Inlet Repair and Replacement
WZTC

## Slide 152
WZTC

## Slide 153: WZTC: Routine Maintenance Focus Areas
Commonly used PATAs and Related Maintenance Activities
Pub. 213 PATA 11d - Stationary, Short-Term Operation, Two-Lane, Two Way Roadway – Road Closure
    Pipe Replacement
    Milling Paving
    Liquid Seal Coat and Surface Treatment
WZTC

## Slide 154
WZTC

## Slide 155: Selecting the Appropriate PATA
Step 1: Understand the requirements of the work activity
    What equipment and materials will you be using?
    To what extent will they be encroaching on the roadway during the operation?
    Will your operation be Stationary or Mobile?
    Check the Foreman’s Manual (Pub.113)
WZTC

## Slide 156: Selecting the Appropriate PATA
Step 2: Be familiar with where you will be working
    What type of roadway is it?
    What is the ADT?
    Are there any unique or unusual traffic patterns?
    Does the location present any problems with sight distance?
    Is closing the road to thru traffic during the operation a possibility?
    Are there any intersections that may warrant special or additional traffic control?
    Will you be required to maintain traffic at an intersection?
    What is the posted or normal speed limit?
WZTC

## Slide 157: Selecting the Appropriate PATA
Before moving on to Step 3 (Selecting a PATA), we need to review definitions associated with some of the terms and references used so far.
Definitions
Short - Term Stationary Operation - Work that occupies a location up to 24 hours. (Ref. Pub. 213 General Notes / Reference Guide)
Long - Term Operations - Work that occupies a location more than 24 hours. (Ref. Pub 213 General Notes / Reference Guide)
WZTC

## Slide 158: Selecting the Appropriate PATA
Definitions
Active work zone - The portion of a work zone where construction, maintenance or utility workers are on the roadway or on the shoulder of the highway, and workers are adjacent to an active travel lane. Workers are not considered adjacent to an open travel lane if they are protected by a traffic barrier and no ingress or egress to the work zone exists through an opening in the traffic barrier. ( Ref. Chapter 212.1 )
Work Zone - The area of a highway where construction, maintenance or utility work activities are being conducted, and in which traffic-control devices are required in accordance with this chapter. ( Ref. Chapter 212.1 )
WZTC

## Slide 159: Selecting the Appropriate PATA
Step 3: Selecting the PATA
  Use the Reference Guide in Publication 213
    Type of Highway
    Condition
    PATA Number
WZTC

## Slide 160
WZTC

## Slide 161
WZTC

## Slide 162
WZTC

## Slide 163
WZTC

## Slide 164
Example
WZTC

## Slide 165: Applying and Maintaining the Selected PATA
Now That You’ve Selected a PATA…
Review the traffic control devices required by the PATA.
Read the notes on the PATA, they are important
Check your inventory of traffic control devices. Do you have all the required signs, cones, paddles, portable sign stands, etc.?
Now that you’re in the process of securing the traffic control devices required under the PATA, is there anything else you need to know about them?
WZTC

## Slide 166: Signs
Do they Meet Department Specifications?
  Clean and in a good state of repair
  “Like new” condition
  Legible
  Highly reflective qualities – day and night
WZTC

## Slide 167: The Setup
Signs must be placed at the proper distance intervals
  Reference: Publication 213, General Notes & PATA
  Review the selected PATA and associated notes
  Signs may be adjusted based on field conditions
WZTC

## Slide 168: The Setup
Signs must be properly ballasted
  Ballasting may be accomplished by placing sandbags on the lower parts of the frame or stay or by storing sand within the hollow components in the bottom of the barricade.
  Block, bricks, large rocks or similar types of material are not permitted to be used as a ballast.
  Sandbags are not permitted to be placed on top of or suspended from signs, rails or any other device.
WZTC

## Slide 169
Signs must be installed correctly.
WZTC

## Slide 170: The Setup
When Required, arrow panels must be of the correct size
  Reference: Pub. 213 General Notes, Table 5
Signs must be visible to approaching traffic
  Signs shall be placed in positions where they will effectively convey their messages. Therefore, their placement shall be accommodated to the highway design and alignment.
  Signs shall also be placed so that drivers will have adequate time for response.
WZTC

## Slide 171
Sign positioned 10 feet from edge of pavement in the weeds.
WZTC

## Slide 172: The Setup
Signs must be clean, legible, and in a good state of repair
Signs must be properly located laterally and at the proper height
  Reference Pub 213, Page 6 of 113, PATA Sign layout
WZTC

## Slide 173
WZTC
Correct sign, properly placed.

## Slide 174: The Setup
Signs shall not obstruct sight distance at driveways, intersections or any existing sign or applicable traffic control device
  Orange flags are NOT required on advance warning signs
WZTC

## Slide 175: The Setup
Flags are optional
Reminder: Pub. 213 represents the minimum requirements.
Flags may be used if it is felt they enhance visibility of signs – (optional).
Be consistent, if flags are used, place them on all signs in the setup.
WZTC
Notes: Foreman should be encouraged to utilize optional flags when they feel it will enhance the safety of the work zone.
Some districts require that flags be used.
When flags are used try to be consistent as not to confuse the motoring Public.

## Slide 176: The Setup
Hand signaling devices are of the appropriate size and type
Taper(s) and longitudinal channelization properly installed. All devices of the same type, properly spaced, and correctly aligned
  Reference: Chapter 212.406 (a) / Pub 213 General Notes Tables 1, 2, and 3
If using barricades, must be of appropriate type and properly striped
WZTC

## Slide 177
WZTC

## Slide 178: Flaggers
Monitor flagger conduct.
Ensure all flaggers have
attended Flagger Training
and are properly attired.
WZTC
Notes: Ensure that the flaggers are where they are supposed to be and that they are monitoring and controlling the traffic flow.

## Slide 179: Flaggers Attire
Helmet/Hard hat
Class 2 garment high visibility yellow with orange stripes
Leggings / Chaps – high visibility yellow
    Daytime optional
    Nighttime required
Class 2 high visibility yellow rain gear in inclement weather
Proper footwear
WZTC
Notes: Equipment is not the only tool available to flaggers to assist them in completing their duties. Proper attire is also critical for safety.
All persons performing flagging work in Pennsylvania are required to wear a protective helmet. In addition to the helmet, PennDOT employees performing flagging duties are required to wear a high-visibility fluorescent yellow-green garment with retroreflective orange stripes that meets performance Class 2 requirements in the ANSI 107-2004 standard. High visibility fluorescent yellow-green pants, leggings or chaps are optional while flagging during the day, but are REQUIRED at night for PennDOT employees. The additional background color and retroreflective material provided in the pants or leggings must ensure that flagger attire satisfies performance Class 3 requirements in the ANSI 107-2004 standard. During inclement weather, high visibility fluorescent yellow-green ANSI Class 2 rain gear may be used. The use of these colors will help provide you with the greatest color contrast with your surroundings. Proper footwear should also be worn by PennDOT flaggers. Ask your foreman or assistant county maintenance manager if you have questions on this attire.

## Slide 180: The Setup
Shadow vehicle used as required and properly positioned
  Reference: Pub 213
When used, warning lights are of appropriate type & correctly placed/positioned
Flaggers properly attired and correctly positioned
  For Department personnel a high visibility pants or leggings are required in combination with high visibility vest and hard hat while flagging at night. Reference: Safety Policy Manual (Pub 445 9-10).
  Reference: Chapter 212.411
WZTC

## Slide 181
Leggings are optional for daylight operations.
WZTC

## Slide 182: The Setup
Initial drive-thru.. All components correct? Any confusion?
Don’t assume that all devices are correctly positioned and all features of your setup are functioning as designed. Make certain that they are.
Drive Thru and put yourself in the position of our customers.
    Does everything make sense?
    Does the advance warning meet the required sight distance?
    Do you feel comfortable with the amount of advance warning?
  If not, you may have to consider adjustments.
  All Distances listed are minimum, not only do you have the right to make adjustments under the law, you have an obligation to do so.
WZTC

## Slide 183: During the Operation
Your Pub. 213 or TCP must be maintained on the work site
  Reference: WZTC QA, Item B.1.
  Be prepared to respond to questions regarding you setup
  Reference: WZTC QA, Item B.11.
Monitor and maintain the integrity of your setup
  Reference: WZTC QA, Item C.2.
WZTC

## Slide 184: During the Operation
Monitor and observe the effectiveness of flagging operations and flagger conduct
  Reference: Flagger Handbook – Pub.234
Be prepared to identify and properly sign and protect the motoring Public from any temporary surface irregularities or potential hazardous conditions that will remain after you vacate the site
  Use “low shoulder”, “no guiderail”, “bump”, or “no pavement marking” signs as needed
WZTC

## Slide 185
WZTC

## Slide 186
WZTC

## Slide 187: Ending the Day’s Operation
If materials and/or equipment are to be stored at or near the site
  30 feet minimum from edge of travel lane
  Behind guide rail or barrier
  2 feet behind curb
  If materials and or equipment stored at site do not meet the above criteria they must be delineated.
WZTC

## Slide 188
Stockpiled construction materials must be placed at least 30 feet from the travel portion of the roadway.
WZTC

## Slide 189: Ending the Day’s Operation
The Closeout Discussion
Involve as many members of your crew as possible in the Work Zone Traffic Control process.
  They see things you don’t
  Their input is critical to improving the quality of all aspects of our field operations
  They can help assure that everyone goes home safe and sound, crew members and customers alike.
WZTC

## Slide 190: Ending the Day’s Operation
If materials and/or equipment are to be stored at or near the site
  30 feet minimum from edge of travel lane
  Behind guide rail or barrier
  2 feet behind curb
WZTC

## Slide 191: Ending the Day’s Operation
The Closeout Discussion
Involve as many members of your crew as possible in the Work Zone Traffic Control process.
  They see things you don’t
  Their input is critical to improving the quality of all aspects of our field operations
  They can help assure that everyone goes home safe and sound, crew members and customers alike.
WZTC

## Slide 192
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety
Reference specific information to improve safety in Department work zones
Be familiar with Publication 213 PATAs and associated common problem areas
Identify the primary topic areas and guidelines in Chapter 212/Publication 213 PATAs/MUTCD
WZTC

## Slide 193
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety
Reference specific information to improve safety in Department work zones
Be familiar with Publication 213 PATAs and associated common problem areas
Identify the primary topic areas and guidelines in Chapter 212/Publication 213 PATAs/MUTCD
We have the responsibility to protect our work force and the motoring Public.
WZTC

## Slide 194
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety
Reference specific information to improve safety in Department work zones
Be familiar with Publication 213 PATAs and associated common problem areas
Identify the primary topic areas and guidelines in Chapter 212/Publication 213 PATAs/MUTCD
The three primary components of a work zone are:
Advanced warning of work area
Specific directions and instructions
Delineation of the work area
WZTC

## Slide 195
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety
Reference specific information to improve safety in Department work zones
Be familiar with Publication 213 PATAs and associated common problem areas
Identify the primary topic areas and guidelines in Chapter 212/Publication 213 PATAs/MUTCD
The 2 most commonly used Publication 213 PATAs for pipe replacement are; Pub. 213 PATA 10a. and Pub. 213 PATA 11d.
WZTC

## Slide 196
Improve focus on Work Zone Traffic Control to reinforce Department’s commitment to safety
Reference specific information to improve safety in Department work zones
Be familiar with Publication 213 PATAs and associated common problem areas
Identify the primary topic areas and guidelines in Chapter 212/Publication 213 PATAs/MUTCD
The primary topic areas needed to determine the correct work zone setup are; “Type of Highway”, “Condition” and Figure Number”.
WZTC

## Slide 198: Quality assurance
Quality Assurance

## Slide 199
Identify and refer to PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
Quality Assurance

## Slide 200: Pipe replacement Quality Control Source Documents
The pipe replacement quality control source documents are:
      Publication 113
      Publication 72M
      Publication 464
      QA review form M-7324
Quality Assurance

## Slide 201: Pub 113
Quality Assurance

## Slide 202: Pub 113
Quality Assurance

## Slide 203: Pub 113
Quality Assurance

## Slide 204: Pub 72M, RC Standards
Quality Assurance

## Slide 205: RC-10
Quality Assurance

## Slide 206: RC-30
Quality Assurance

## Slide 207: Pipe replacement Quality Control
Source Documents
    Publication 464 applicable Best Maintenance Practices (BMPs):
      1 Seeding
      2 Mulching
      3 Rock Stabilization
      6 Surface Preparation
Quality Assurance

## Slide 208
Quality Assurance

## Slide 209
Quality Assurance

## Slide 210
Quality Assurance

## Slide 211
Quality Assurance

## Slide 212: Pipe replacement Quality Control
Source Documents
    Quality Assurance Review Form QA – M-7324
Quality Assurance

## Slide 213
Quality Assurance

## Slide 214: Quality Assurance Pipe Replacement Operations
The Q A Process Identifies Those Components or Elements of an Operation Required to Realize an Objective. The Objective Here…Quality Pipe Replacement.
Each Element Consists of Indicators Representing Levels of Performance in the Execution or Completion of a Given Element:
Each Element is Then Grouped Into One of Three Categories:
  most critical
  moderately critical
  nominally critical
Quality Assurance

## Slide 215
Quality Assurance
Pipe Replacement Operations
Category A: Elements grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.
Category B: Elements grouped into this category are representative of functions Deemed moderately critical to the overall quality and longevity of the finished product. Unlike category A, “marginal” performance on a given element in this category (although not desirable), will in all likelihood not contribute directly to the immediate failure or shortened life span of the finished product.
Category C: Elements grouped into this category are representative of functions deemed nominally critical to the overall quality and longevity of the finished product. Unlike category B, “less than marginal” performance (although not desirable), will not contribute to the premature failure of the finished product.
Quality Assurance

## Slide 216: Category A
Category A:
First group of quality assurance elements
The elements that are grouped into this category are representative of functions deemed most critical to the overall quality & longevity of the finished product
Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span
Quality assurance
Notes: The first group of quality assurance elements belongs to Category A. The elements that are grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.

## Slide 217: Category A
1. Flow Line
2. Inlet/Outlet Flow Established
3. Backfill
4. Compaction
5. PA 1-Call
6. Location/Length
7. Trench Width
Quality assurance
Notes: The first group of quality assurance elements belongs to Category A. The elements that are grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.

## Slide 218
A. 1. Flow Line (Ref. Pub 113, Pub 408 Sec. 601)
1. Improper slope.
3. Grade line slightly irregular, with minimum slope of ¼” of fall per foot overall.
5. Uniform slope of ¼” or greater of fall per foot.
Quality Assurance
Pipe Replacement Operations
¼” of Fall/Ft. or > Overall
Vertical Alignment is True
Note that ¼” per foot is the “Minimum” Fall per Foot
Quality Assurance

## Slide 219
Quality Assurance
Pipe Replacement Operations
Outlet ditch completely blocked. Additional ditch cleaning required.
Inlet partially restricted.
2. Inlet/Outlet Flow Established
1. Inlet and/or outlet ditches restricted > 30%.
3. Inlet and/or outlet ditch partially restricted <30%.
5. Inlet and outlet ditches open with no restrictions.
Quality Assurance

## Slide 220
Quality Assurance
Pipe Replacement Operations
Approved backfill material is 2A aggregate
Material should most desirably be at or near its’ optimum moisture content value….(it should be damp but with no water running from it).
Field test by compressing in hands in the shape of a ball. If material retains shape when hands are opened, the material is suitable for use.
A. 3. Backfill * (Ref. Pub 113, Pub 408 Sec. 601)
1. Using existing excavated or improper material; or placing backfill in loose lifts exceeding 8” in depth prior to compaction.
3. Proper material placed in loose lifts of 4” to 8” in depth prior to compaction.
5. Proper material placed in loose lifts no greater than 4” in depth prior to compaction or 8” loose lifts compacted with a vibratory roller.
Quality Assurance

## Slide 221
A. 3. Backfill (cont’d.)
Quality Assurance
Pipe Replacement Operations
Introducing Backfill to the Trench
Material introduced to the trench via Backhoe
Material introduced to the trench via skid-steer loader.
Utilization of the skid-steer loader on Pipe Replacement Operations has been identified as a “best practice” and rightfully so.
Skid-steer loaders are very versatile, require a much smaller work platform than the Backhoe and afford the crew an opportunity to continue with excavation while introducing backfill.
Production is increased and efficiency enhanced thru the use of skid-steer loaders…especially in those situations where traffic is detoured and the roadway closed to thru traffic.
Quality Assurance

## Slide 222
A. 3. Backfill
Quality Assurance
Pipe Replacement Operations
Use of Flowable Fill
Ready-mixed flowable fill is commonly a blend of cement, fly ash, sand, and water. Typically it is designed as a low strength, flowable material requiring no subsequent vibration or tamping to achieve 100% consolidation.
Considerations when used as bedding/backfill in pipe replacement operations:
* Pipe must be held in a stable position of alignment both vertically and horizontally during the introduction of material
* Pipe must be elevated from the bottom of the excavation to allow fill material to completely surround the pipe.
* Pipe trench must be encapsulated to prevent the material from escaping the trench.
Quality Assurance

## Slide 223
Quality Assurance
Pipe Replacement Operations
A. 4. Compaction * (Ref. Pub 113, RC-30, Pub 408 Sec. 601)
1. No compaction or compaction effort terminated while extensive backfill movement remained beneath compaction device(s).
3. One upright compactor used, backfill material moist and compaction effort extended till little or no evidence of backfill movement remained beneath the compaction device.
5. Two upright compactors or vibratory roller used, backfill material moist and compaction effort extended till little or no evidence of backfill movement remained beneath the compaction device and compaction devices were not used directly over the centerline of the pipe until the depth of fill reached 12”
Quality Assurance

## Slide 224
A. 4. Compaction
Quality Assurance
Pipe Replacement Operations
Initial compaction effort
Backfill depth < 12” over pipe
Backfill depth 12” and > over pipe
Compactors should be operated in tandem to avoid moving the pipe out of horizontal alignment
No compaction directly over the top of the pipe until the depth of backfill over the pipe is 12” and >
Compaction effort directed over the full width of the trench after depth of backfill is 12” and > over the top of the pipe
Quality Assurance

## Slide 225
A. 4. Compaction
Quality Assurance
Pipe Replacement Operations
The compaction effort is complete when there is little or no evidence of movement of the backfill material beneath the compaction device(s)
Satisfactory Compaction
Quality Assurance

## Slide 226
Quality Assurance
You Want to Know This Gas Line is There “Before” you Begin to Excavate !!!
Know the Law !!!!!
Pipe Replacement Operations
5. PA 1-Call (Ref. PA-1 CALL)
1. No PA 1-Call made as prescribed by law or excavation begun prior to three working days after placing the PA 1-Call.
3. PA 1-Call made but excavation begun outside the prescribed time frame. (Ten working days beyond notification date ).
5. PA 1-Call made as prescribed by law, work conducted within the prescribed time frame and related PA 1-Call documentation on site ( copy of notification form w/registration # or documentation with notification date & registration # ).
Quality Assurance

## Slide 227
A. 5. PA 1-Call (cont’d.)
Quality Assurance
Pipe Replacement Operations
Who Should Make the Call?
All contractors, including sub-contractors, should make their own notification.
Contractor Responsibilities
To provide a One Call System with specific information to identify the site so that facility owners might provide indications of their lines.
A contractor shall use the color “white” to mark a proposed excavation site when exact site information cannot
be provided.
Notification shall be not less than three nor more than ten working days in advance of beginning excavation or demolition work.
Site: The specific place where excavation or demolition work is being or is planned to be performed.
Working Day: A working day means any day except a Saturday and Sunday or a legal holiday prescribed by
the act of the General Assembly.
Quality Assurance

## Slide 228
A. 5. PA 1-Call (cont’d.)
Quality Assurance
Pipe Replacement Operations
Disruption of any one of these services can adversely impact day to day life, and unexpectedly finding any one of these during an excavation operation without having made the required notification can be very costly, both in terms of human life and $.
Quality Assurance

## Slide 229
A. 6. Location/Length
Quality Assurance
Pipe Replacement Operations
1. Pipe including any inlet, endwall or end section does not meet the alignment and grade line and does not meet the slope / flowline intercept.
3. Pipe including any inlet, endwall or end section meets the alignment and grade line of the watercourse but does not extend beyond the slope / flowline intercept.
5. Pipe including any inlet, endwall or end section meets the alignment and grade line of the watercourse and extends beyond the slope / flowline intercept for a distance of 1’ or a distance sufficient to insure or improve the stability of the slope.
Quality Assurance

## Slide 230
A. 6. Location/Length (cont’d.)
Quality Assurance
Pipe Replacement Operations
This pipe was replaced at the same elevation as the original pipe. The inlet end is under less than 12” of cover. Lowering the outlet end 18” and extending it would have stopped the ongoing erosion of the slope.
Quality Assurance

## Slide 231
A. 7. Trench Width **
Quality Assurance
Pipe Replacement Operations
** Width measured from band or bell to trench wall. Additional width permitted for safety to protect workers. Additional width is also acceptable as a means of accommodating water along one side of the trench during installation.
Insufficient trench width means insufficient compaction.
It can also result in damage to the pipe. The operator attempted to force the compactor by the bell of the pipe and in doing so, the pipe was spalled.
Width of this Tamper Foot was 10”
Sufficient trench width is determined by measuring here.
1. Too narrow. Insufficient width to allow for compaction equipment on both sides of the pipe for the entire length of the installation.
3. Too wide. Greater than 4’ wider than the outside diameter of the pipe.
5. Sufficient width. Width from 2’ to 4’ greater than the outside diameter of the pipe.
Quality Assurance

## Slide 232
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
10”
10”
12”
Maximum performance when operated in a vertical position.
Trench too narrow to allow compactor to be operated in a vertical position.
Impact value is maximized and energy properly directed when operated in vertical position.
10”
14”
90
26”
Quality Assurance

## Slide 233
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
10”
10”
12”
10”
14”
90
26”
Maximum performance when operated in a vertical position.
Trench too narrow to allow compactor to be operated in a vertical position.
Impact value is decreased and energy is misdirected.
Quality Assurance

## Slide 234
Excavator bucket deflection resulting from resistance.
x
Width of Cut on Surface
Y
Width at planned elevation of installation. (Midpoint of pipe)
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
Horizontal Deflection During Excavation
Width of cut on surface
Trench width at planned elevation of installation. (Midpoint of pipe)
This Type of Horizontal Deflection is a Common Occurrence During Excavation. Is it a Problem?
It can be… if your trench width calculations simply included the greatest outside dimension of the pipe and to it you added 2’ (1’ on each side of the pipe), and failed to recognize the deflection that routinely occurs, you will have insufficient width at the point of installation (midpoint of the pipe), as illustrated above.
Is There a Standard Formula That I Can Apply to Determine How Wide The Width of Cut on the Surface Should Be?
Because of all of the variables such as soil types, depth of excavation, length of excavation, and different types of excavation equipment, there is no one-size-fits-all formula. Your determination of width of cut on surface should consider: soil type; depth of excavation; greatest outside dimension of the pipe; length of the excavation; and required clear width on each side of the pipe at the planned installation elevation (by spec. This can be up to 2’).
Quality Assurance

## Slide 235
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
As a rule, horizontal deflection cannot be eliminated during excavation, but it is possible to minimize it if:
Horizontal Deflection During Excavation
Remove bituminous wearing and base course.
Begin excavation against trench wall.
Continue excavation against adjacent trench wall.
Excavate material from center of trench. Repeat sequence (2. Thru 4.)
( 1. )
( 2. )
( 3. )
( 4. )
You’re using a backhoe to do the excavation
The width of the trench on surface is 60” or >
Beginning excavation in the center of the trench increases the extent to which horizontal deflection will occur along the trench wall
Lateral resistance
Lateral Resistance
No Lateral Resistance
Quality Assurance

## Slide 236
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
It Won’t Fit……
Trench width was adequate
Pipe not placed true to the centerline of the trench
If the first section is incorrectly positioned and backfilled, the entire installation will be skewed
Very likely that this will be the end result..Here, no compaction will be possible for a distance of approximately 8’ on one side of the pipe.
What Happened?
Be certain alignment is true “before” placement and backfilling begins.
Quality Assurance

## Slide 237
A. 7. Trench Width (cont’d.)
Quality Assurance
Pipe Replacement Operations
Considerations in Determining Trench Width:
Greatest outside diameter of pipe to be installed
Depth of the excavation, specifically to the midpoint or springline of the pipe being installed
Nature of the soil to be excavated
Length of the excavation
Is Kilroy going to be operating the backhoe again?!@!#!
Quality Assurance

## Slide 238: Category B
Category B:
Second group of quality assurance elements
The elements that are grouped into this category are representative of functions deemed moderately critical to the overall quality & longevity of the finished product
Marginal performance on a given element in this category, although not desirable, will not in all likelihood directly contribute to the immediate failure or shortened life span of the finished product
Quality assurance
Notes: 238
The second group of quality assurance elements belongs to Category B. The elements that are grouped into this category are representative of functions deemed moderately critical to the overall quality and longevity of the finished product. Unlike Category A, a marginal performance on a given element in this category, although not desirable, will not in all likelihood directly contribute to the immediate failure or shortened life span of the finished product.

## Slide 239: Category B
Category B Elements:
  End Treatment
2. Bedding
3. Joints
4. Cover
5. Grade Control
6. E. & S. Controls
7. Waste Disposal
8. Trench Stability
Quality assurance

## Slide 240
B. 1. End Treatment
Quality Assurance
Pipe Replacement Operations
SHOULDER
Encroachment into the established shoulder area most frequently occurs when constructing or installing endwalls or headwalls on drainage systems that run diagonally to the centerline of the roadway.
1. Not properly aligned (parallel), with edge of roadway, no end treatment applied, or established width of the shoulder restricted by placement too close to edge of pave.
3. Stone headwall only.
4. Properly constructed stone headwall and endwall.
5. Concrete, masonry, pre-fabricated plastic or treated timber headwall; gabion basket; drop inlet or flared end section. Installed or scheduled and properly aligned (parallel) with edge of roadway and established shoulder width not restricted.
Quality Assurance

## Slide 241
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
Some standard and not so standard approaches
Formed in place and pre-cast drop inlets
Loosely placed field and mountain stone
Plastic Endwalls
Quality Assurance

## Slide 242
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
Some standard and not so standard approaches
Stone Masonry
Stacked 90Lb. Bags of Quikrete
Cement Block
Quality Assurance

## Slide 243
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
A unique, quick, and unconventional approach to drop inlet construction
The opening was contoured to fit around the exterior of a section of 18” RCCP
The section of 36” plastic pipe was previously cut to a predetermined length
Quality Assurance

## Slide 244
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
A unique, quick, and unconventional approach to drop inlet construction
With the concrete pipe in position in the trench, crew members position the plastic pipe over the inlet end. The upright section of plastic rests on an 8” bed of compacted 2A aggregate.
Quality Assurance

## Slide 245
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
A unique, quick, and unconventional approach to drop inlet construction
The installation is backfilled and compacted with 2A aggregate in 8” lifts to grade.
If you consider this method of drop inlet construction, it is recommended that the point of entry be sealed around the circumference of the concrete pipe prior to backfilling and that a concrete floor be poured in the bottom of the installation to a depth equal to the flow line of the concrete pipe.
Quality Assurance

## Slide 246
B. 1. End Treatment (cont’d.)
Quality Assurance
Pipe Replacement Operations
A unique, quick, and unconventional approach to drop inlet construction
An approved, bicycle safe circular drop inlet grate is installed and the area around the installation is paved at the time trench restoration is completed.
This type of installation should always be placed in the flow line and never be placed on the traveled portion of the shoulder.
Quality Assurance

## Slide 247
Quality Assurance
Pipe Replacement Operations
B. 2. Bedding ***
1. No bedding or insufficient depth…< 6” or no cradle where required.
3. Sufficient depth…> 6” – improper material, or proper material installed to a depth > 6” but compacted where compaction/consolidated is not required/warranted.
5. Sufficient depth…> 6” – proper material used and cradle installed where required. End sections compacted as required.
*** Proper bedding material – Concrete pipe – 1B and 2A, all others 2A or OGS material. Cradle required with squash/elliptical pipe equal in depth to 15% of the vertical rise of the pipe.
Quality Assurance

## Slide 248
Quality Assurance
Pipe Replacement Operations
B. 2. Bedding (cont’d.)
“Bedding” minimum depth 6”
Loosely placed 2A aggregate
Roadway Wearing Course Base Course
Plastic & CMP Pipe (Round)
6” is the “minimum” bedding depth.
To address contour irregularities in the trench bed, use an 8” bedding depth in your installation plan….Nobody digs a perfect trench.
Quality Assurance

## Slide 249
Quality Assurance
Pipe Replacement Operations
B. 2. Bedding (cont’d.)
“Bedding” minimum depth 6”
Loosely placed 2A aggregate
Cradle
Cradle height equal to 15% of vertical rise of pipe
x
Roadway Wearing Course Base Course
CMP (Elliptical)
6” is the “minimum” bedding depth.
To address contour irregularities in the trench bed, use an 8” bedding depth in your installation plan….Nobody digs a perfect trench.
Quality Assurance

## Slide 250
Quality Assurance
Pipe Replacement Operations
B. 2. Bedding (cont’d.)
“Bedding” minimum depth 6”
Loosely placed 1B aggregate “outlet end section bedded on compacted 2A”
Cradle
Cradle height equal to 15% of vertical rise of pipe
x
Roadway Wearing Course Base Course
6” is the “minimum” bedding depth.
To address contour irregularities in the trench bed, use an 8” bedding depth in your installation plan….Nobody digs a perfect trench.
Concrete (Elliptical)
Quality Assurance

## Slide 251
Quality Assurance
Pipe Replacement Operations
B. 2. Bedding (cont’d.)
“Bedding” minimum depth 6”
Loosely placed 1B aggregate “outlet end section bedded on compacted 2A”
Minimum depth of bedding beneath bell = 2”
Roadway Wearing Course Base Course
Concrete (Round)
6” is the “minimum” bedding depth.
To address contour irregularities in the trench bed, use an 8” bedding depth in your installation plan….Nobody digs a perfect trench.
A recess must be formed in the bedding to receive the bell. Pipe must be supported by the pipe barrel.
Quality Assurance

## Slide 252
B. 2. Bedding *** (cont’d.)
Quality Assurance
Pipe Replacement Operations
*** Proper bedding material – Concrete pipe – 1B and 2A, all others 2A or OGS material. Cradle required with squash/elliptical pipe equal in depth to 15% of the vertical rise of the pipe.
2A bedding material placed at outlet end
Bedding material compacted
Additional 2A added and cradle shaped w/ rake
Quality Assurance

## Slide 253
B. 3. Joints
Quality Assurance
Pipe Replacement Operations
Concrete Pipe Installation Sequence
Tongue and Groove
Flow
Groove
Installation to Begin at the Outlet End
Quality of Joint Improved When Gravity is Working With You
Bell and Spigot
Bell
Flow
Spigot
Tongue
Bell
Spigot
Create Recess in Bedding to Receive Bell
Tongue
Groove
1. No joint material; caulk, mortar, mastic or bands used as warranted by the pipe installed.
3. Improper sealant or mismatched bands.
4. Slight misalignment ( vertical or horizontal ). Approved sealant and/or bands used.
5. Pipes properly joined.
Quality Assurance

## Slide 254
B. 3. Joints cont.
Quality Assurance
Pipe Replacement Operations
Rolled pipe joint mastic
Unroll, press into place, remove paper backer
Pipe joint compound (5 gal. Buckets)
Troweled into place
Quality Assurance

## Slide 255
B. 3. Joints (cont’d.)
Quality Assurance
Pipe Replacement Operations
Plastic bands secured with nylon draw straps. Bands are constructed to match the exterior contour (valleys and ridges) of the pipe used. Always wear gloves.
Metal bands secured with nuts and bolts. During the process of tightening the bands, periodic tapping will be necessary to insure a snug fit. A rubber mallet should be used to avoid damage to the galvanized coating. Always wear gloves.
Do Not Use Steel Hammers
Quality Assurance

## Slide 256
B. 4. Depth of Cover
Quality Assurance
Pipe Replacement Operations
Minimum Cover Over Pipe is 1’ (12”)
This measurement is taken from the greatest vertical dimension of the pipe at the band or bell to the elevation of the roadway surface
If lowering the flow line of the replacement pipe to acquire the required cover (12”) is not possible, assuming the intent was to install a round pipe, consideration should be extended to installing an elliptical or squash pipe of equal carrying capacity.
Reducing the size of the replacement pipe to acquire the required cover should be avoided.
In some situations, acquiring the required cover over the replacement installation may not be possible. However, every effort should be made to exhaust all practical possibilities to secure the required cover.
1. Less than 1’ of cover where possible to attain.
5. Greater then 1’of cover or not possible to attain.
Quality Assurance

## Slide 257
35”
21”
28”
42”
49”
18”
18”
27”
B. 4. Depth of Cover (cont’d.)
Quality Assurance
Pipe Replacement Operations
24”
34”
40”
36”
54”
48”
42 1/2”
55 3/4”
22 1/4”
30”
35 3/4”
46 3/4”
42”
59 3/4”
TYPE OF PIPE
I.D.
O.D. (BARREL)
O.D. (BELL)
I.D. SPAN RISE
O.D. SPAN RISE
ELIPTICAL AND ARCH PIPE
Concrete Standard Bell & Spigot (Round)
49 1/4”
29”
30”
42”
42 1/2”
55 3/4”
22 1/4”
36”
24”
48”
49 1/4”
29”
35 3/4”
Concrete Tongue & Groove (Round)
Concrete Tongue & Groove (Elliptical)
25 1/4”
19 1/4”
33”
33”
40 3/4”
29 3/4”
20”
29”
48 1/2”
35 1/2”
33”
56 1/4”
40 1/4”
21”
15”
35”
24”
28”
42”
57”
38”
64 3/4”
45 3/4”
Corrugated Metal “CMP” (Round)
Corrugated Metal “CMP” (Arch)
48”
36”
24”
18”
30”
42”
20 1/2”
26 1/2”
33”
39”
45”
51”
15”
24”
49”
38”
57”
20”
29”
33”
23 1/2”
17 1/2”
30 1/2”
22 1/2”
38”
27”
45”
32”
52”
36”
60”
41”
Plastic “Polyethylene” (Round)
18”
30”
36”
24”
22”
26”
32 3/4”
36”
Equivalent Round Size:
18”
24”
36”
48”
42”
30”
Equivalent Round Size:
18”
30”
42”
48”
36”
24”
Commonly used pipe and related dimensions
Quality Assurance

## Slide 258
B. 5. Grade Control
Quality Assurance
Pipe Replacement Operations
1. No instruments used in determining and/or controlling the installed depth and slope of the replacement pipe or carpenters level used.
3. Line level used to determine and control the installed depth and slope of the replacement pipe.
5. Locke level, dumpy level or transit used in determining and controlling the installed depth and slope of the replacement pipe.
Quality Assurance

## Slide 259
B. 5. Grade Control (cont’d.)
Quality Assurance
Pipe Replacement Operations
The key word is “control”. It begins here during the initial field inspection.
Quality Assurance

## Slide 260
B. 5. Grade Control (cont’d.)
Quality Assurance
Pipe Replacement Operations
Placement of the pipe
Control continues thru each phase of the pipe replacement operation.
Excavation
Placement of Bedding
Quality Assurance

## Slide 261
6. E & S Controls “Environmental Conduct (Ref.Pub.113, “711-7324” & Pub.23, Chap.3, pg.16)
Quality Assurance
Pipe Replacement Operations
Erosion & Sedimentation
1. No erosion and/or sedimentation control measures taken as required.
5. Erosion and/or sedimentation control measures taken as required.
Quality Assurance

## Slide 262
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Seeding
Mulching
Quality Assurance

## Slide 263
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Rock Lining
Hay/Straw Bales
Silt Fence
Erosion and sedimentation controls are only effective if properly installed and maintained
Quality Assurance

## Slide 264
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Seeding
DEFINITION:
The establishment of a permanent vegetative cover on disturbed areas using rapidly growing plants.
PURPOSE:
Seeding with various grass or grass and leguminous plant mixtures necessary to restore vegetative cover to soil surfaces exposed during excavation operations. Restoring the vegetative cover with deep-rooted, long lived and persistent adapted plant species is the most effective measure to prevent extensive soil erosion and any accompanying sediment loss and deposit in undesired areas. The use of permanent seeding or mulching must be anticipated during all earthwork operations.
Applications, methods and procedures
Permanent seeding and mulching shall be placed when project areas are constructed to finish grade.
Mulch or ecb (erosion control blankets) must always be applied after seed has been applied. Apply in accordance with the applicable best management practice for the materials selected.
In situations where there is not an opportunity for seed to germinate and establish, use mulch or ecbs for temporary stabilization.
Compost must be applied if all soil containing grass roots is removed.
Sow seeds uniformly on the prepared areas by helicopter, hydraulic placement, broadcasting, drilling, or hand seeding methods. Inspect seeding equipment and adjust if required to assure the specified application rates. Periodically perform a check on the rate and uniformity of application.
Quality Assurance

## Slide 265
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Seeding formula descriptions, rates of application and seeding dates
Seeding Formula
Description
Seeding Rate kg per 1000 m2 (lbs. Per SY)
Seeding Dates
Formula B
A refined lawn type generally used on non-steep surfaces where a more highly maintained and mowed surface is desired. Use only on areas which have topsoil.
11.5 (21.0)
March 15 to June 1 August 1 to October 15
Formula C
Generally used on slopes steeper than 3:1 where mowing is not anticipated or desired. Topsoil application is not necessary, do not use within 6.1 meters (20 feet) of areas where evergreen trees, shrubs, seedlings, or vines are to be planted. Crownvetch will hinder the invasion of adjacent native vegetation for many years.
5.0 (9.0)
Ryegrass: March 1 to October 15
Crownvetch: March 1 to October 15
Formula D
Generally used on most highway slope areas not receiving Formula C where mowing may or may not be designated. Normally used in drainage channels or swales requiring permanent seeding.
11.5 (21.0)
March 15 to June 1 August 1 to October 15
Formula E
Generally used to quickly stabilize exposed soil surfaces because it generally germinates within 2 weeks in favorable climate conditions. Considered most often for temporary use on unfinished graded areas during construction since the life cycle averages 1 – 2 years.
5.5 (10.0)
March 15 to October 15
Formula L
Can be used on low maintenance slope areas which are not mowed and on flatter areas that are mowed 2 times per year or less. Should not be mowed to a height less than 150 mm (6 inches). Not very adaptive to wet soil conditions.
13.0 (24.0)
March 15 to June 1 August 1 to October 15
Formula W
Can be used on a wide assortment of conditions from fairly dry to fairly wet soils wheere non-mow conditions are desired, such as wetland replacement areas or wildlife habitat areas.
5.5 (10.5)
April 1 to June 15 August 16 to Sept. 15
Most commonly applied formulas in drainage related activities
Quality Assurance

## Slide 266
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Seeding
Applications, Methods and Procedures
When seed (generally formulas b, d, and l) is applied to areas that will be mowed (slopes 3:1 or flatter), topsoil should be used. Refer to PennDOT Pub. 408 for general installation guidelines.
Spread seed within seeding dates identified for the formula used. If conditions warrant, the dates may be extended. If extended, either apply full treatment or apply 50% of permanent seeding and soil supplements and apply the remaining 50% within the next seeding dates.
In critical areas such as those adjacent to or within 15 meters (50 feet) of streams, ponds, or wetlands, use a protective blanket for seeded areas. Seeded areas on slopes steeper than 3:1 shall be covered with protective blankets…reference Pub. 464 “maintenance field reference for erosion and sediment controls” for erosion control blanket (ecb) types and application methods and procedures.
When wetland areas are temporarily disturbed, isolate and stockpile topsoil for replacement after grading is complete. If temporary vegetative stabilization is necessary, apply annual ryegrass at the rate of 22 kilograms (48 pounds) pls. Mulch using clean straw at the rate of 7200 kilograms per hectare (3 tons per acre). Soil amendments are not needed.
Vegetated areas are considered permanently stabilized when a uniform 70% perennial vegetative cover has been achieved, or the disturbed area is covered with an acceptable bmp(erosion and sediment control “best management practice”.
Refer to PennDOT Pub. 464 “maintenance field reference for erosion and sediment controls” for additional application information as well as alternative and companion best management practices related to seeding.
Quality Assurance

## Slide 267
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Mulching
Definition:
Temporary cover of plant material used to control erosion and sediment, or used during seeding for stabilization and to propagate initial seed growth.
Purpose:
Absorb rainfall impact, increase the rate of infiltration, reduce soil moisture loss due to evaporation, moderate soil temperatures, provide a suitable environment for seed germination, and protect the seedling from intense sunlight.
Applications, Methods and Procedures
Mulch or erosion control blankets (ecbs) must always be placed over seeded areas.
In areas where the slope is 3:1 or greater erosion control blankets are to be used….Not mulch.
Mulches specified in the table below can be used alone as temporary stabilization in areas where there is no opportunity for seed to germinate and establish. Apply mulches at the rate shown in the table.
Mulch is to be placed immediately after seeding.
App. Rate (Min.)
kg Per 1000 m2
lbs Per 1000 SY
Temporary Stabilization
Notes
Mulch Type
Straw
Hay
Pelletmulch
650
650
293
1,200
1,200
320
Either wheat or oat straw, free of weeds, not chopped or finely broken.
Timothy, mixed clover and timothy, or other native forage grasses.
Thoroughly wet with water after applying.
Yes
Yes
No
Quality Assurance

## Slide 268
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Maintaining seeding and mulching
* Maintenance and inspection of the installation must be continued until the site is permanently stabilized.
* The installation should be inspected after each runoff event until permanent stabilization is realized.
* If the installation fails to perform as expected, the situation must be addressed immediately with alternative erosion and sedimentation best management practices or modifications of those installed. Reference Pub. 464 “maintenance field reference for erosion and sediment controls”
* Perform all required preventive and remedial maintenance work, including clean-out, repair, replacement, re-grading, reseeding, re-mulching, and re-netting immediately following inspection.
Quality Assurance

## Slide 269
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Outlet Protection
Definition:
An energy dissipater constructed in the area of an outfall to provide scour protection for discharges from pipes and channels.
Purpose:
To prevent erosion in areas immediately downstream of pipe and channel outlets.
Applications, Methods And Procedures
Place outlet protection at the outlet of any concentrated flow, such as outlets of storm drains, ponds, temporary slope pipes, ditches, or other conveyances.
Two types of outlet protection (rock basins and rock energy dissipaters) are presented in PennDOT Pub. 464 “maintenance field reference for erosion and sediment controls”. This training package will address “rock energy dissipaters”. Reference Pub. 464 for details relative to the application, methods and procedures associated with “rock basins”.
Quality Assurance

## Slide 270
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Outlet Protection “Rock Energy Dissipater”
FLOW
E
E
FLOW
PIPE END TREATMENT AS REQUIRED
D
D
TRANSITION INTO EXISTING DRAINAGE CHANNEL
PLAN VIEW
4.5 m (15 ft.)
R-7 ROCK
600 mm (2 ft.)
3.0 m (10 ft.)
SLOPE 1.5 : 1
R-5 ROCK
CLASS 2, TYPE A GEOTEXTILE LINING
CLASS 2, TYPE B GEOTEXTILE LINING
600 mm (2 ft.)
FINISH SLOPE AS REQUIRED
SECTION D-D
900 mm (3 ft.) MIN.
4.5 m (15 FT.)
3.0 m (10 FT.)
600 mm (2 ft.)
900 mm (3 ft.) MIN.
CLASS 2, TYPE A GEOTEXTILE LINING
SECTION E-E
SLOPE 1.5 : 1
Quality Assurance

## Slide 271
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Maintaining Rock Energy Dissipaters
* Maintenance and inspection of the installation must be continued until the site is permanently stabilized.
* The installation should be inspected after each runoff event until permanent stabilization is realized.
* If the installation fails to perform as expected, the situation must be addressed immediately with alternative erosion and sedimentation best management practices or modifications of those installed. Reference Pub. 464 “maintenance field reference for erosion and sediment controls”
* Perform all required preventive and remedial maintenance work, including clean-out, repair, replacement, re-grading, and reshaping immediately following inspection.
* If scour is discovered at the outlet, enlarge the size of the stone or energy dissipater to protect the eroded area.
Quality Assurance

## Slide 272
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Cross Section
8’ Maximum center to center
36” minimum length post, driven a minimum of 18” into ground (posts are 2” by 2” wood or equivalent)
15” minimum height of filter fabric (geotextile, class 3)
6” Minimum depth in ground
FLOW
FLOW
FLOW
POST SECTION MAXIMUM 18” ABOVE GROUND
FILTER FABRIC EMBEDED A MINIMUM OF 6” VERTICALLY INTO GROUND
FILTER FABRIC
POST DRIVEN A MINIMUM OF 18” INTO GROUND
UPSTREAM PERSPECTIVE
PLAN VIEW
POSTS
STAPLE
STAPLE
JOINING TWO ADJACENT SILT FENCE SECTIONS
UNDISTRUBED GROUND
BACKFILL TO BE COMPACTED
Standard Silt Barrier (18” High)
Both ends of each fence section should extend at least 2.4 m (8 feet) upslope at 45 degrees to the main fence alignment.
Silt barrier fence should be at least 2.4 m (8 feet) from the toe of fill slopes
Quality Assurance

## Slide 273
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Standard And Reinforced Silt Barrier Fence
Definition:
Temporary barrier of entrenched geotextile (filter fabric) stretched across and attached to supporting posts, which is used to remove sediment from runoff from disturbed areas.
Purpose:
Controls sheet flow runoff from disturbed areas where discharge is to a stable area.
Do not use silt barrier fence in areas of concentrated flow such as channels, swales, erosion gullies, across pipe outfalls, or as inlet protection.
Install downslope of all disturbance in existing ground, and parallel to existing contours.
Maximum Slope Length Above Fence
18” High Fence (Standard)
30” High Fence (Reinforced)
Slope Percent
2 (or less)
5
10
15
20
25
30
35
40
45
50
45 m (150 ft.)
30 m (100 ft.)
15 m (50 ft.)
10 m (35 ft.)
8 m (25 ft.)
6 m (20 ft.)
4.5 m (15 ft.)
4.5 m (15 ft.)
4.5 m (15 ft.)
3 m (10 ft.)
3 m (10 ft.)
150 m (500 ft.)
75 m (250 ft.)
45 m (150 ft.)
30 m (100 ft.)
20 m (70 ft.)
17 m (55 ft.)
14 m (45 ft.)
12 m (40 ft.)
11 m (35 ft.)
9 m (30 ft.)
8 m (25 ft.)
Maximum Up-Slope Length
Quality Assurance

## Slide 274
Quality Assurance
Pipe Replacement Operations
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
UPSTREAM PERSPECTIVE
8’ MAXIMUM CENTER TO CENTER
48” MINIMUM LENGTH POST, DRIVEN A MINIMUM OF 18” INTO GROUND (POSTS ARE 2” BY 2” WOOD OR EQUIVALENT)
30” MAXIMUM HEIGHT OF FILTER FABRIC (GEOTEXTILE, CLASS 3)
6” MINIMUM DEPTH IN GROUND
FLOW
FLOW
PLAN VIEW
POSTS
STAPLE
STAPLE
JOINING TWO ADJACENT SILT FENCE SECTIONS
FLOW
FILTER FABRIC (MESH REINFORCED)
REINFORCED SILT BARRIER (30” HIGH) (MESH REINFORCED)
CLASS 3 GEOTEXTILE FABRIC
REINFORCING MESH
CUTAWAY VIEW
EITHER INDUSTRIAL POLYPROPOLENE OR STEEL MESH WITH 150mm (6”) MAX. OPENING STEEL MESH SHALL BE 14 GA. MIN.
CROSS SECTION
POST SECTION MAXIMUM 30” ABOVE GROUND
FILTER FABRIC EMBEDED A MINIMUM OF 6” VERTICALLY INTO GROUND
POST DRIVEN A MINIMUM OF 18” INTO GROUND
UNDISTRUBED GROUND
BACKFILL TO BE COMPACTED
25mm x 50mm x 300mm (1” x 2” x 12”) STAKES
* MIN. 10 GA. WIRE
* In Reinforced Silt Barrier Fence, Attach Upslope Guy Wires to the Side of the Stakes or Place a Continuous Row of Staked Bales.
Quality Assurance

## Slide 275
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
8’ MAXIMUM CENTER TO CENTER
48” MINIMUM LENGTH POST, DRIVEN A MINIMUM OF 18” INTO GROUND (POSTS ARE 2” BY 2” WOOD OR EQUIVALENT)
30” MAXIMUM HEIGHT OF FILTER FABRIC (GEOTEXTILE, CLASS 3)
6” MINIMUM DEPTH IN GROUND
FLOW
FLOW
UPSTREAM PERSPECTIVE
PLAN VIEW
POSTS
STAPLE
STAPLE
JOINING TWO ADJACENT SILT FENCE SECTIONS
CROSS SECTION
FLOW
POST SECTION MAXIMUM 30” ABOVE GROUND
FILTER FABRIC EMBEDED A MINIMUM OF 6” VERTICALLY INTO GROUND
FILTER FABRIC (MESH REINFORCED)
POST DRIVEN A MINIMUM OF 18” INTO GROUND
UNDISTRUBED GROUND
BACKFILL TO BE COMPACTED
REINFORCED SILT BARRIER (30” HIGH) (STRAW BAIL SUPPORTED)
STRAW BAILS – INSTALLED CONTINUOUSLY AGAINST DOWNSLOPE SIDE OF SILT BARRIER FENCE
TWO SUPPORT STAKES REQUIRED PER BAIL.
Quality Assurance

## Slide 276
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
10’ MAXIMUM CENTER TO CENTER
72” MINIMUM LENGTH POST, PLACED A MINIMUM OF 36” INTO GROUND (POLES ARE 2 ½” DIAMETER GALVANIZED STEEL OR ALUMINUM )
33” MAXIMUM HEIGHT OF FILTER FABRIC (GEOTEXTILE, CLASS 3)
8” MINIMUM DEPTH IN GROUND
FLOW
FLOW
UPSTREAM PERSPECTIVE
CROSS SECTION
FLOW
POLE SECTION MAXIMUM 36” ABOVE GROUND
FILTER FABRIC EMBEDED A MINIMUM OF 8” VERTICALLY INTO GROUND
FILTER FABRIC (CLASS 3 GEOTEXTILE)
POLE DRIVEN A MINIMUM OF 36” INTO GROUND
UNDISTRUBED GROUND
BACKFILL TO BE COMPACTED
HEAVY DUTY SILT FENCE
WOVEN WIRE FENCE
NO. 7 GA. TENSION WIRE
150 mm (6 in) MIN.
AT JOINTS BOTH ENDS OF FABRIC SHOULD BE OVERLAPPED A MINIMUM OF 150 MM (6 INCHES), FOLDED AND SECURED TO THE FENCE.
POLE
FASTENERS
WOVEN WIRE FENCE
GEOTEXTILE, CLASS 3
(GEOTEXTILE JOINING AND FASTENING)
FASTENERS
NO. 7 GA. TENSION WIRE
PLAN VIEW
Quality Assurance

## Slide 277
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Heavy Duty Silt Barrier Fence
Definition:
A temporary barrier of entrenched geotextile (filter fabric) backed with chain link fence with both stretched across and attached to supporting posts. Super (heavy duty) silt fence is used to remove sediment from runoff drainage areas when the maximum slope lengths for reinforced silt fence cannot be met and sufficient room for construction of sediment traps or basins does not exist.
Purpose:
Controls sheet flow runoff from disturbed areas where discharge is to a stable area.
Do not use silt barrier fence in areas of concentrated flow such as channels, swales, erosion gullies, across pipe outfalls, or as inlet protection.
Install downs lope of all disturbance in existing ground, and parallel to existing contours.
Heavy Duty Silt Fence
Maximum Up-Slope Length
Slope Percent
2 (or less)
5
10
20
30
40
50
300 m (1000 ft.)
150 m (500 ft.)
90 m (300 ft.)
60 m (200 ft.)
30 m (100 ft.)
25 m (75 ft.)
15 m (50 ft.)
Quality Assurance

## Slide 278
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Maintaining Silt Barrier Fence
* Maintenance and inspection of the installation must be continued until the site is permanently stabilized.
* The installation must be inspected after each runoff event.
* If the installation fails to perform as expected, the situation must be addressed immediately with alternative erosion and sedimentation best management practices or modifications of those installed. Reference Pub. 464 “maintenance field reference for erosion and sediment controls”
* Perform all required preventive and remedial maintenance work, including clean-out, repair, and replacement immediately following inspection.
* Sediment must be removed when accumulations reach ½ the above ground height of the fence. Dispose of sediment in stockpile behind silt barrier fence, stabilizing with seed or other methods.
* Undermined or topped sections must be immediately replaced with a rock filter outlet.
Quality Assurance

## Slide 279
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
FLOW
4” VERTICAL FACE
FLOW
TO ANCHOR BAILS TOGETHER, ANGLE FIRST STAKE TOWARD PREVIOUSLY LAID BAIL
BEDDING DETAIL
BOUND BALES (NOTE POSITION OF BINDING)
2” X 2” X 36” STAKES DRIVEN A MINIMUM OF 18” IN GROUND. STAKES ARE TO BE DRIVEN FLUSH WITH THE TOP OF THE BALES
COMPACTED BACKFILL
POSTS DRIVEN A MINIMUM OF 18” INTO GROUND
18”
STRAW BAIL BARRIERS
COMPACTED BACKFILL
Quality Assurance

## Slide 280
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Straw Bale Barriers
Definition:
A temporary barrier consisting of a row of entrenched and anchored straw bales or similar material used to remove sediment from runoff from small areas of disturbed soil.
Purpose:
Straw bales may be used only in applications involving sheet flow and for durations lasting less than 3 months.
Do not use straw bale barriers in areas of concentrated flow such as channels, swales, erosion gullies, across pipe outfalls, or as inlet protection.
Install down slope of all disturbance in existing ground, and parallel to existing contours.
Straw Bale Barriers
Maximum Up-Slope Length
Slope Percent
2 (or less)
5
10
15
20
25
30
46 m (150 ft.)
30 m (100 ft.)
15 m (50 ft.)
11 m (35 ft.)
8 m (25 ft.)
6 m (20 ft.)
5 m (15 ft.)
35
40
45
50
5 m (15 ft.)
5 m (15 ft.)
3 m (10 ft.)
3 m (10 ft.)
Quality Assurance

## Slide 281
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Maintaining Straw Bale Barriers
* Maintenance and inspection of the installation must be continued until the site is permanently stabilized.
* The installation must be inspected after each runoff event.
* If the installation fails to perform as expected, the situation must be addressed immediately with alternative erosion and sedimentation best management practices or modifications of those installed. Reference Pub. 464 “maintenance field reference for erosion and sediment controls”
* Perform all required preventive and remedial maintenance work, including clean-out, repair, and replacement immediately following inspection.
* Sediment must be removed when accumulations reach 1/3 the above ground height of the straw bale
* Undermined or topped sections must be immediately replaced with a rock filter outlet.
* Sediment deposits left after removal of barriers should be contoured to the existing grade and seeded.
Quality Assurance

## Slide 282
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Rock Filter
Definition:
Small, temporary, stone filter dams installed across a channel or swale.
Purpose:
The primary purpose of a rock filter is to remove sediment from flows in a channel.
Applications, methods and procedures
Rock filters may be used below construction work within an existing stream while flow is being diverted past the work area.
Rock filters should not be used in channels less than 0.3 meters (1 foot) in depth.
Do not use geotextile lining or straw bales in, or with, rock filters.
To construct a rock filter determine the required length for the ditch or depression. Place rock evenly with a minimum of voids.
Construct filters equal in height to half the total depth of the channel.
The center depression shall be equal to ½ the filter height or 15 millimeters (6 inches), whichever is less.
Place a 0.3 meter (1 foot) thick layer of ASHTO #57 aggregate on the upstream side of the filter.
Immediately upon stabilization of the channel, remove the accumulation of sediment, use rock from filter as outlet protection, and stabilize the disturbed areas.
Quality Assurance

## Slide 283
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
FLOW
1
2
2
1
.
1 : 1
PROFILE
0.3 m. (1 ft.)
DITCH BOTTOM
150 mm (6 in.)
ROCK (SEE TABLE BELOW)
AASHTO #57
ROCK FILTER
CROSS SECTION CENTERLINE LOOKING UPSTREAM
ROCK SIZE
Channel Total Depth
Rock Size
Greater than 0.9 m (3 ft.)
R-4
0.6 m to 0.9 m (2 ft to 3 ft)
0.3 m to 0.6 m (1 ft to 2 ft)
Less than 0.3 m (1 ft)
R-3
R-2
Do not use rock filter
150 mm (6 in) OR ½ FILTER HEIGHT (WHICHEVER IS LESS)
0.3 m (1 ft) MIN.
FILTER HEIGHT SHOULD EQUAL ½ THE TOTAL DEPTH OF THE CHANNEL
TOP OF CHANNEL
Quality Assurance

## Slide 284
B. 6. E & S Controls “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Maintaining Rock Filters
* Maintenance and inspection of the installation must be continued until the site is permanently stabilized.
* The installation must be inspected after each runoff event.
* If the installation fails to perform as expected, the situation must be addressed immediately with alternative erosion and sedimentation best management practices or modifications of those installed. Reference Pub. 464 “maintenance field reference for erosion and sediment controls”
* Perform all required preventive and remedial maintenance work, including clean-out, repair, and replacement immediately following inspection.
* During inspection, observe if water is eroding around the sides of the rock filter. If so, address immediately.
* Remove sediment when accumulation reaches ½ the height of the filters at the center depression.
Quality Assurance

## Slide 285
B. 7. Waste Disposal “Environmental Conduct” (Ref.Pub.113, “711-7324” & Pub.23, Chap.3, pg.16)
Pipe Replacement Operations Generate Three Different Types of Waste:
Excavated Earth and Stone
Bituminous Materials
Metal….Routinely in the Form of Excavated Corrugated Metal Pipe
1. Excavated earth, stone and/or bituminous materials disposed on non-Department owned property and no release (M-666) secured or release secured and site on which materials are deposited exhibits obvious wetland characteristics, or steel reinforced concrete and excavated corrugated metal pipe not segregated from excavated earth, stone and bituminous materials prior to disposal, or project-related litter and debris left on site.
5. Excavated earth, stone and bituminous materials properly disposed, required releases (M-666) secured and on site, steel reinforced concrete and scrap metal segregated from excavated earth, stone and bituminous materials prior to disposal, steel reinforced concrete and scrap metal properly disposed or stored for scrap sale or recycling and site is free of project-related litter and debris. Environmental due diligence forms completed as required.
Quality Assurance
Quality Assurance
Pipe Replacement Operations

## Slide 286
B. 7. Waste Disposal “Environmental Conduct” (cont’d.)
Excavated Earth & Stone
Excavated Metal Pipe
Excavated Bituminous Material
Quality Assurance
Quality Assurance
Pipe Replacement Operations

## Slide 287
B. 7. Waste Disposal “Environmental Conduct” (cont’d.)
It All Adds Up!
Pipe Replaced During Fiscal year 2001-2002 …..
216,000 Feet
(Approximately 41 Miles of Pipe)
* Excavated Material Requiring Disposal:
Earth and Stone – 150,000 Cubic Yards
Bituminous Material – 18,000 Tons
Metal Pipe – 918 Tons
6,818 Tri-Axle Dump Truck Loads (22 c.y. capacity)
If Lined up End to End – 38Miles
This Amount of Bituminous Material Would Cover 18 Miles of Roadway 20 Feet Wide at an Inch and a Half in Depth
* Estimates Assume the Following:
900 Tri-Axle Dump Truck Loads (22 c.y. capacity)
Trench Width 5’; Total Trench Depth 4 ½’; Depth of Bituminous Pavement Removed 5”; Total Length of Pavement Removal Equal to 50% of Pipe Placed; Length of Pipe Removed Equal to 85% (183,600’) of Pipe Replaced (216,000’); All Pipe Removed was Metal; O.D. of Pipe Removed 15”; Weight per Foot of Pipe Removed 10 Lbs.
102 Tri-Axle Dump Truck Loads (22 c.y. capacity)
Quality Assurance
Quality Assurance
Pipe Replacement Operations

## Slide 288
B. 7. Waste Disposal “Environmental Conduct” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Releases Secured
Metal Properly Disposed of or Stored
Worksite Clean and Free of All Project Related Debris and Waste
Quality Assurance

## Slide 289
B. 8. Trench Stability “Worker Safety Element” (N/A . Not Applicable. Score This Element “N/A” When Not Warranted ) (Ref. Pub.113, Chap.9, table 4.1 & 4.2)
Quality Assurance
Pipe Replacement Operations
OSHA Requirements
Trenches over 5 feet in depth must be shored trenches less than 5 feet in depth should be shored if hazardous ground movement may be expected
Ladders placed in all trenches over 4 feet in depth (spaced at 25 feet)
Side rails of ladder extending 3 feet above trench
All materials, tools and equipment to be stored a minimum 2 feet back of trench edge
1. Safety measures relative to shoring requirements required but not taken.
5. Adequate measures taken to insure trench wall stability where required.
Quality Assurance

## Slide 290
B. 8. Trench Stability “Worker Safety Element” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Approximate Angle of Repose for Sloping Sides of Excavations
Presence of Ground Water Requires Special Treatment
Clays, Silts, Loams, & Non-Homogenous Soils Require Shoring & Bracing
Well Rounded Loose Sand 2 : 1
Compacted Sharp Sand 1-1/2 : 1
Average Soils 1 : 1 (45o )
Compacted Angular Gravels 1/2 : 1
Solid Rock or Shale Vertical (90o )
Quality Assurance

## Slide 291
B. 8. Trench Stability “Worker Safety Element” (cont’d.)
Quality Assurance
Pipe Replacement Operations
Shoring and Shielding
Quality Assurance

## Slide 292: Category C
Category C:
Third group of quality assurance elements
The elements that are grouped into this category are representative of functions deemed nominally critical to the overall quality & longevity of the finished product
Less than marginal performance on a given element in this category, although undesirable, will not contribute to the premature failure of the finished product
Quality assurance
Notes: 292
The third, and final, group of quality assurance elements belongs to Category C. The elements that are grouped into this category are representative of functions deemed nominally critical to the overall quality and longevity of the finished product. Unlike Category B, less than marginal performance on a given element in this category, although not desirable, will not contribute to the premature failure of the finished product.
Let’s get started with Category C.

## Slide 293: Category C
Category C Elements:
Pavement Cutting
2. Size
3. Damaged Pipe
4. Unsuitable Material
5. Horizontal Pipe Alignment
Quality assurance

## Slide 294
C. 1. Pavement Cutting
Quality Assurance
Pipe Replacement Operations
Concrete Saw
Jackhammer
Vermeer Wheel
Pizza Wheel
Cutoff Saw
Tools of the Trade
1. Not cut.
2. Pavement cut– Adjacent surface damaged during excavation.
3. Uneven or partial depth cut. No damage to adjacent pavement during excavation.
5. Uniform, full depth cut. No damage to adjacent pavement during excavation.
Quality Assurance

## Slide 295
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
End Product of a Partial Depth Cut
Actual Depth of Pavement Varied from 6” to 8” in Depth
Saw Cut Depth was 3 ½” to 4”
Adjacent Pavement Severely Fractured and Faulted
A Cutoff Saw was Used
Maximum Cut Depth is 4” w/ 12” Blade; 5” w/14” Blade; and 6” w/16” Blade
Dolly Mounted Cutoff Saw
Quality Assurance

## Slide 296
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Bituminous wearing and base course
Saw cut to full depth of bituminous wearing and base course
Saw Cuts Straight and Parallel
Saw cuts extend to full depth of pavement for entire width of pavement including shoulders if paved
Subbase
Objective: Removal of bituminous material with minimal or no damage to the adjacent pavement surface
Quality Assurance

## Slide 297
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Pavement cut to full depth
Excavation begins with careful removal of the bituminous surface
Quality Assurance

## Slide 298
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Adjacent Pavement Faulted During Excavation
Causes:
Pavement Not Cut to Full Depth
Excavator Operator Overly Aggressive at Onset of Excavation
Pavement Surfaces Bound During Excavation Because Angle of Attack Slightly Diagonal to Saw Cut
Adjacent Pavement Damage During Initial Phase of Excavation
Quality Assurance

## Slide 299
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Concrete Saw
Guaranteed Full Depth Pavement Cut
Support Requirements:
Water Supply
Trailer
Additional Personnel
Cut Depths from 12” to 18”
Quality Assurance

## Slide 300
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Pneumatic Hammer (Jackhammer)
Bit must be chisel faced
Pointed
Chiseled face to be directed to inside of trench
Inside of trench
Very labor intensive
Pavement depths of 4” and greater are rarely cut to their full depth
Adjacent pavement always fractured using this method
Inside of Trench
Material displaced… not cut
Displacement exaggerated with pointed bit
Quality Assurance

## Slide 301
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Pizza Cutter
C-Clamp configured scoring wheel. designed to be attached to the bucket of a front end loader or the blade of a grader
Minimal penetration 2 ½” to 3”
Adjacent surfaces severely faulted
Lines scored in pavement are erratic (not straight)
This is the least desirable method of “cutting” the pavement over the trench.
Quality Assurance

## Slide 302
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Vermeer Cutting Wheel Mounted on Bobcat
Cutting depth up to 18”
Cuts through concrete & ½” re-bar
Use of the Bobcat-mounted Vermeer Wheel has been identified as a “best practice” in addressing pavement cutting requirements on pipe replacement operations.
Quality Assurance

## Slide 303
Vermeer Wheel in Operation
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Quality Assurance

## Slide 304
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Pavement depth was 6”
Width of pavement 18’
Cutting time: 30 seconds
Quality Assurance

## Slide 305
C. 1. Pavement Cutting (cont’d.)
Quality Assurance
Pipe Replacement Operations
Loose material swept back into open kerfs
Width of kerf approximately 5”
No binding w/adjacent pavement during initial excavation of paved surface over trench
Quality Assurance

## Slide 306
C. 2. Pipe Size
Quality Assurance
Pipe Replacement Operations
Any activity involved in maintaining something in “good working order”
Maintenance:
Performance indicators recognize increased storm water runoff generated by changes in land use over the past 20 to 40 years
Performance indicators also recognize current laws relative to storm water management
Most pipe requiring replacement today were originally installed 20 to 40 years ago
Replacing a 15” pipe in kind rarely addresses these changes
Replacing this 15” pipe “in kind” may not represent maintaining the facility in “good working order”
1. Reduced size of existing pipe or installed pipe > 48” dia. without hydraulic study.
3. Replaced 15” in kind.
5. Installed 18” to 48” dia. pipe or > 48” dia. pipe with hydraulic study.
Quality Assurance

## Slide 307
C. 3. Damaged Pipe
Quality Assurance
Pipe Replacement Operations
Care must be taken during transportation, storage and placement
Most vulnerable to damage are concrete and metal pipe
1. Damaged ends and/or holes in pipe.
2. Damaged ends and/or major unrepaired coating damage.
3. No end damage – minor unrepaired coating damage.
4. No end damage – coating damage repaired.
5. No visible damage.
Quality Assurance

## Slide 308
C. 3. Damaged Pipe (cont’d.)
Quality Assurance
Pipe Replacement Operations
Mortar mix used to repair damage
Concrete pipe damaged by excavator bucket during installation
Quality Assurance

## Slide 309
C. 3. Damaged Pipe (cont’d.)
Quality Assurance
Pipe Replacement Operations
Damage to galvanized CMP routinely occurs as a result of careless handling or improper installation procedures
Do not use steel hammers
At galvanized surfaces, apply organic zinc repair paint complying with requirements of ASTM A 780. Galvanizing repair paint shall have 95 percent zinc by weight. Thickness of applied galvanizing repair paint shall be not less than coating thickness required by ASTM A 123 or A 153 as applicable. Touch-up of galvanized surfaces with aerosol spray, silver paint, bright paint, brite paint, or aluminum paints is not acceptable.
Repair of Damaged Galvanized Coating
Damage to galvanized coating accelerates corrosion and shortens the life expectancy of the installation
Quality Assurance

## Slide 310
C. 4. Unsuitable Material
Quality Assurance
Pipe Replacement Operations
Unsuitable Material
Material containing debris, organic matter, frozen material or large stones with a diameter greater than one half the thickness of the compacted layers being placed *.
“Planned Depth” of Trench
Unsuitable Material Encountered
Additional Excavation Required
Remove unsuitable material to a minimum depth of 12” below the “planned depth” of the trench
Backfill and compact with suitable material (2A aggregate), in loose lifts not exceeding 8” in depth to the “planned depth” of the trench.
* Stone Greater Than 4” in Diameter
Pipe Trench
1. Unsuitable material not removed.
3. Unsuitable material removed to an insufficient depth….> 6” but < 12”.
4. Unsuitable material removed to proper depth in accord with RC-30 and replaced with suitable material compacted to grade in loose lifts exceeding 8” in depth.
5. Unsuitable material removed to proper depth in accord with RC-30 and replaced with suitable material properly compacted to grade in loose lifts not exceeding 8” in depth.
Quality Assurance

## Slide 311
C. 5. Horizontal Pipe Alignment
Quality Assurance
Pipe Replacement Operations
Vertical Axis
Horizontal Axis
Horizontal Alignment “Appears” to be Relatively True
Some Vertical Misalignment “Apparent”
Target Should Appear Equally Segmented Here
1. No daylight visible through pipe.
2. > 3” deviation in alignment.
3. Minor misalignment (< 3” deviation).
5. No discernable misalignment.
Quality Assurance

## Slide 312
Identify the PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
  “Most Critical Items”,
  “Moderately Critical Items”, and
  “Nominally Critical Items”
Quality Assurance

## Slide 313
Identify the PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
  “Most Critical Items”,
  “Moderately Critical Items”, and
  “Nominally Critical Items”
Quality assurance information for pipe replacement can be found in; Publication 113 (Highway Foreman Manual), Roadway Construction Standards 10 and 30, Publication 464 (Erosion and Sedimentation Best Practices) and the Pipe Replacement Quality Assurance Review Form.
Quality Assurance

## Slide 314
Identify the PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
  “Most Critical Items”,
  “Moderately Critical Items”, and
  “Nominally Critical Items”
Category A, Most Critical Items include:
  Flow-line
  Inlet/outlet flow-line established
  Backfill
  Compaction
  Backfill
  Worker safety
  Pipe location
  Trench width
Quality Assurance

## Slide 315
Identify the PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
  “Most Critical Items”,
  “Moderately Critical Items”, and
  “Nominally Critical Items”
Category B, Moderately Critical Items include:
  End treatments
  Bedding
  Pipe joints
  Depth of cover
  Grade control
  Environmental conduct
  Trench stability
Quality Assurance

## Slide 316
Identify the PennDOT Publications relative to a quality pipe installation project
Identify the applicable information from each Publication
Demonstrate a working familiarity with the Pipe Replacement Quality Assurance Review Form
  “Most Critical Items”,
  “Moderately Critical Items”, and
  “Nominally Critical Items”
Category C, Nominally Critical Items include:
Pavement cutting
Pipe size
Damaged pipe
Unsuitable materials in trench
Pipe alignment
Quality Assurance

## Slide 318: Environmental concerns
Environmental Concerns

## Slide 319
Identify and refer to the PennDOT source documents that relative to environmental stewardship during pipe replacement operations
Identify potential environmental concerns associated with pipe replacement operations
Select and initiate corrective action for environmental concerns identified
Understand proper erosion and sedimentation control practices
Demonstrate a working familiarity with the Environmental Stockpile Review
Environmental Concerns

## Slide 320: Environmental Policies & Regulations Source Documents
Publication 464, “Maintenance Field Reference for Erosion and Sedimentation Control”
Publication 113, “Highway Foreman’s Manual”
Publication 23, “PennDOT Maintenance Manual”
M-7324, “Pipe Replacement Quality Assurance Form”
Environmental Concerns

## Slide 321: Environmental Policies & Regulations Source Documents
Environmental Concerns
Back

## Slide 322: Environmental Policies & Regulations Source Documents
Environmental Concerns
Back

## Slide 323: Environmental Policies & Regulations Source Documents
Environmental Concerns
Back

## Slide 324: Environmental Policies & Regulations Source Documents
Environmental Concerns
Back

## Slide 325: Environmental Policies & Regulations Publication 464
Identifies BMPs required for Pipe Replacement Activities
Defines and describes activities associated with:
    S T. 1 . SEED Seeding
    S T. 2 . MLCH Mulching
    S T. 3 . ROCK Rock Stabilization
Environmental Concerns

## Slide 326: Environmental Policies & Regulations Publication 464
Identifies BMPs required for Pipe Replacement Activities
Defines and describes activities associated with:
    S T. 1 . SEED Seeding
    S T. 2 . MLCH Mulching
    S T. 3 . ROCK Rock Stabilization
The establishment of a vegetative cover, permanent or temporary, on disturbed areas using rapidly growing plants.
Environmental Concerns

## Slide 327: Environmental Policies & Regulations Publication 464
Identifies BMPs required for Pipe Replacement Activities
Defines and describes activities associated with:
    S T. 1 . SEED Seeding
    S T. 2 . MLCH Mulching
    S T. 3 . ROCK Rock Stabilization
Temporary cover of various organic and non-organic materials used to control erosion and sediment, or used during seeding for stabilization and to propagate initial seed growth.
Environmental Concerns

## Slide 328: Environmental Policies & Regulations Publication 464
Identifies BMPs required for Pipe Replacement Activities
Defines and describes activities associated with:
    S T. 1 . SEED Seeding
    S T. 2 . MLCH Mulching
    S T. 3 . ROCK Rock Stabilization
Using rock or coarse aggregate to stabilize an eroded or washed out area of a slope, channel, or outfall.
Environmental Concerns

## Slide 329: Environmental Policies & Regulations
PENNDOT’S Green Plan Policy
As a direct result of our commitment to assuring adequate, safe and efficient intermodal transportation facilities and services at reasonable cost to the citizens of the Commonwealth of Pennsylvania, the Department of Transportation will play a leading role in the administration of environmental responsibility. The Department will demonstrate this leadership by committing to the following principles relative to the planning, design, construction, operation and maintenance of Pennsylvania’s balanced intermodal transportation system.
Principle 1. Plan, design, build, operate and maintain a statewide transportation system that protects the environment, prevents pollution and uses resources efficiently.
Principle 2. Contribute to economic vitality and quality of life by applying sound environmental management practices which address the requirements of the public, users, carriers, industry and labor.
Principle 3. Comply with applicable environmental legislation and regulations.
Principle 4. Establish a program of review and continual improvement of environmental performance which accounts for technical and economic developments, scientific understanding, and significant environmental impacts.
Principle 5. Establish relevant and measurable objectives which endeavor to improve environmental performance and provide the means to gauge progress.
Principle 6. Ensure employees understand these principles as well as their priority, and are furnished with the means to fulfill them.
These principles are essential elements for the management of the Department as we enter the 21st century. As part of a fully integrated environmental management system, these principles should be incorporated into the policies, programs and practices of all Department of Transportation organizations.
Environmental Concerns

## Slide 330: Environmental Policies & Regulations
Publication 113
Identifies special provisions for maintenance organizations affected by bog turtle habitat
and
Describes methods for disposal of waste material
Environmental Concerns

## Slide 331: Environmental Policies & Regulations
Publication 113
Identifies special provisions for maintenance organizations affected by bog turtle habitat
and
Describes methods for disposal of waste material
Environmental Concerns

## Slide 332: Environmental Policies & Regulations
Publication 23, Chapter 3
Communicates Department Erosion and Sedimentation Control Policy (Chapter 3.12)
Illustrates Erosion and Sedimentation Control Procedures for PennDOT Maintenance Activities (Figure 3.12.1)
Describes the Erosion and Sedimentation Control Plan for Routine Maintenance Activities
Environmental Concerns

## Slide 333: Environmental Policies & Regulations
Publication 23, Chapter 3
Communicates Department Erosion and Sedimentation Control Policy (Chapter 3.12)
Illustrates Erosion and Sedimentation Control Procedures for PennDOT Maintenance Activities (Figure 3.12.1)
Describes the Erosion and Sedimentation Control Plan for Routine Maintenance Activities
Environmental Concerns

## Slide 334: Environmental Policies & Regulations
Quality Assurance (QA) Review Form
  Category B.6. - Erosion and Sedimentation
  Category B.7. - Waste disposal
  For a complete review of the Quality Assurance Evaluation for Pipe Replacement please see the Quality Assurance Module of this training program.
Environmental Concerns

## Slide 335
Quality Assurance, Erosion & Sedimentation
Rock lining to minimize erosion
Environmental Concerns

## Slide 336
Straw bales and silt fence help minimize sedimentation only when properly installed and maintained
Quality Assurance, Erosion & Sedimentation
Environmental Concerns

## Slide 337
Excavated Earth & Stone
Excavated Metal Pipe
Excavated Bituminous Material
Quality Assurance, Waste Disposal
Environmental Concerns

## Slide 338: Additional Environmental Concern
Use of equipment near waterways
  Have spill kits available for emergency spills
  Train personnel for spill emergencies
  Conduct drills
Environmental Concerns

## Slide 339
Identify and refer to the PennDOT source documents that relative to environmental stewardship during pipe replacement operations
Identify potential environmental concerns associated with pipe replacement operations
Select and initiate corrective action for environmental concerns identified
Understand proper erosion and sedimentation control practices
Demonstrate a working familiarity with the Environmental Stockpile Review Form
Environmental Concerns

## Slide 340
Identify and refer to the PennDOT source documents that relative to environmental stewardship during pipe replacement operations
Identify potential environmental concerns associated with pipe replacement operations
Select and initiate corrective action for environmental concerns identified
Understand proper erosion and sedimentation control practices
Demonstrate a working familiarity with the Environmental Stockpile Review Form
Publication 464, “Maintenance Field Reference for Erosion and Sedimentation Control”
Publication 113, “Highway Foreman’s Manual”
Publication 23, “PennDOT Maintenance Manual”
M-7324, “Pipe Replacement Quality Assurance Form”
Environmental Concerns

## Slide 341
Identify and refer to the PennDOT source documents that relative to environmental stewardship during pipe replacement operations
Identify potential environmental concerns associated with pipe replacement operations
Select and initiate corrective action for environmental concerns identified
Understand proper erosion and sedimentation control practices
Demonstrate a working familiarity with the Environmental Stockpile Review Form
Seeding
Mulching
Rock Stabilization
Environmental Concerns

## Slide 342
Identify and refer to the PennDOT source documents that relative to environmental stewardship during pipe replacement operations
Identify potential environmental concerns associated with pipe replacement operations
Select and initiate corrective action for environmental concerns identified
Understand proper erosion and sedimentation control practices
Demonstrate a working familiarity with the Environmental Stockpile Review Form
Environmental Concerns

## Slide 344: Risk management
Risk Management

## Slide 345
Identify potential tort liabilities associated with pipe replacement activities
Risk Management

## Slide 346: Areas of Significant Risk
PA 1-Call
Work Zone Traffic Control
Trench Restoration
Proper Storage of Equipment and Material
Risk Management

## Slide 347: Risk Management
PA 1- Call
  Failure to initiate
  Work started before three days from call or after ten days
  Appropriate paperwork not on site
811
Know what's below,
Call before you dig.
Risk Management

## Slide 348: Risk Management
Work Zone Traffic Control
  Signing
    Failure to use the correct PATA
    Failure to continuously maintain work zone setup
Risk Management

## Slide 349: Risk Management
Work Zone Traffic Control
  Signing
    Failure to use the correct PATA
    Failure to continuously maintain work zone setup
Risk Management

## Slide 350: Risk Management
Work Zone Traffic Control
  Maintaining traffic in the work area
    Encroachment of equipment into travel lanes
    Flaggers
    Use of steel plates
Risk Management

## Slide 351: Risk Management
Trench restoration
  Improperly compacted trenches
    Excessive settlement
  Failure to restore pipe trench
    Loose aggregate
    Failure to maintain until permanently restored
  Failure to delineate pipe trenches and inlets
Risk Management

## Slide 352: Risk Management
Proper storage of equipment and material within the work area
      out of the work zone
      pre-stocking of equipment and material (30 feet from roadway)
Material is stocked too close to roadway.
Risk Management

## Slide 353
Identify potential tort liabilities associated with pipe replacement activities.
Risk Management

## Slide 354
Identify potential tort liabilities associated with pipe replacement activities.
Potential risks associated with pipe replacement include:
WZTC signing
Maintaining traffic in work zone
Improperly compacted trenches
Failure to restore pipe trench
Use of steel plates
Delineation of the pipe trench
Proper storage of equipment within the work area
Risk Management

## Slide 356: Project wrap-up
Project wrap-up

## Slide 357
Identify activities that must be performed at the completion of a pipe replacement activity.
  At the worksite
  At the assembly area
  At the office
Project wrap-up

## Slide 358: Project Wrap-up At the Work Site
Delineate trench and inlet
Clean work site
Remove/turn WZTC signing
Project wrap-up

## Slide 359: Project Wrap-up At the Assembly Area
Dispose of waste properly
Clean and properly store equipment
Prepare for next day’s activities
Project wrap-up

## Slide 360: Project Wrap-up Administrative Duties
Complete payroll
Review, approve, and input payroll
Enter data and notes
File documents for future reference
Project wrap-up

## Slide 361
Identify activities that must be performed at the completion of a pipe replacement activity.
Project wrap-up

## Slide 362
Identify activities that must be performed at the completion of a pipe replacement activity.
Activities that must be performed at the completion of a pipe replacement activity include:
Trench and inlet delineation
Clean work site
Remove/turning WZTC signing
Complete payroll
Review, approve, and input payroll
Data entry, notes, etc.
File Documents for Future Reference
Project wrap-up

## Slide 364: Follow-up activities
Follow-up Activities

## Slide 365
Identify actions needed after the activity is completed to ensure that the completed work functions as designed.
Follow-up Activities

## Slide 366: Follow-up Pipe Replacement Activities
Field view during inclement weather to ensure the entire drainage facility functions
Follow-up Activities

## Slide 367: Follow-up Pipe Replacement Activities
Check after rain events to see if there is water standing on the roadway, schedule follow-up actions as required
Follow-up Activities

## Slide 368: Follow-up Pipe Replacement Activities
Monitor environmental issues
  Additional mulching if needed
  Monitor seeded areas for growth
  Maintain rock filters
  Maintain silt fences
  Removal silt fences and other E&S devices when no longer needed
Follow-up Activities

## Slide 369: Follow-up Pipe Replacement Activities
Permanent replacement of temporary maintenance features
  Permanent pipe trench restoration
  Place headwalls, inlets, etc.
Follow-up Activities

## Slide 370: Follow-up Pipe Replacement Activities
Permanent replacement of temporary maintenance features (continued):
  Click here to go to the Pipe Trench Restoration Training Module.
Follow-up Activities

## Slide 371: Follow-up Pipe Replacement Activities
Complete follow-up activities as required by permits issued by DEP/COE (Corps of Engineers)
Follow-up Activities

## Slide 372: Follow-up Activities
Identify and communicate overall Best Management Practices (BMPs)
Follow-up Activities

## Slide 373
Identify actions needed after the activity is completed to ensure that the completed work functions as designed.
Follow-up Activities

## Slide 374
Identify actions needed after the activity is completed to ensure that the completed work functions as designed.
Actions needed after the activity is completed to ensure that the completed work functions as designed include:
Field view during inclement weather to ensure the entire drainage facility functions
Environmental issues/Pub 464 requirements
Permanent replacement of temporary maintenance features
Record retention (Authorization to Enter, EDD form, etc.)
Follow-up activities required by permits issued by DEP/COE (Corps of Engineers)
Identify and communicate overall drainage best management practices (BMPs)
Follow-up Activities

## Slide 376: Pipe Trench Restoration
Trench restoration

## Slide 377
Understand how to plan and schedule for a pipe trench restoration project.
Identify all of the components of a pipe trench restoration Quality Assurance Review.
Understand how properly perform a pipe trench restoration project.
Trench restoration

## Slide 378: Planning and Scheduling For Pipe Trench Restoration
Source documents that are helpful for conducting pipe trench restoration activities include:
  Publication 113, Highway Foreman Manual
  M-7121 TR, Trench Restoration Quality Assurance Review Evaluation
Trench restoration

## Slide 379
Trench restoration
BACK

## Slide 380
Trench restoration
BACK

## Slide 381: Planning and Scheduling For Pipe Trench Restoration
Planning for a pipe trench restoration project is not difficult but it is important.
Pipe trenches not properly restored can:
  Create a traffic hazard for motorists
  Result in poor ride quality
  Reflect through surface improvement projects
Trench restoration

## Slide 382: Planning For Pipe Trench Restoration
Trench restoration must be planned in conjunction with every pipe installation project.
Trench restoration

## Slide 383: Planning For Pipe Trench Restoration
Trench restoration should be conducted as soon as possible after the pipe installation to minimize tort liability and improve the ride quality of the roadway.
Trench restoration

## Slide 384: Planning For Pipe Trench Restoration
Trench restoration is planned by tons.
Trench restoration

## Slide 385: How many tons are needed?
Material needs for pipe trench restoration can be determined using the following steps:
Sample formula
  Length (FT.) X Width (FT.) X Depth (IN.) /150 = Tons of material.
  A good rule of thumb add 10% to qty. just to be sure.
  Example
  40 FT. x 7 FT. x 4 IN. = 1,120 / 150 = 7.47 Tons
Trench restoration

## Slide 386
Guidelines for proper crew size can be found in Publication 113
Trench restoration

## Slide 387
Guidelines for proper crew size can be found in Publication 113
Trench restoration

## Slide 388
Standard Crew Size
Standard Equipment List
Pub 113
Assembly Requirements for
Pipe Replacement
Production Standards
Trench restoration

## Slide 389
Pub 113
Assembly Requirements for
Pipe Replacement
Trench restoration
Standard Crew Size
Standard Equipment List
Production Standards

## Slide 390
Pub 113
Assembly Requirements for
Pipe Replacement
Trench restoration
Standard Crew Size
Standard Equipment List
Production Standards

## Slide 391
Pub 113
Assembly Requirements for
Pipe Replacement
Trench restoration
Standard Crew Size
Standard Equipment List
Production Standards

## Slide 392: Pipe Trench Restoration
Source Documents
Quality Assurance Review Form M-7121 TR
Trench restoration

## Slide 393: Pipe Trench Restoration
Source Documents
Quality Assurance Review Form M-7121 TR
Trench restoration

## Slide 394
Quality Assurance
Pipe Trench Restoration Operations
Category A: Elements grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.
Category B: Elements grouped into this category are representative of functions Deemed moderately critical to the overall quality and longevity of the finished product. Unlike category A, “marginal” performance on a given element in this category (although not desirable), will in all likelihood not contribute directly to the immediate failure or shortened life span of the finished product.
Trench restoration

## Slide 395: Category A
Category A:
First group of quality assurance elements
The elements that are grouped into this category are representative of functions deemed most critical to the overall quality & longevity of the finished product
Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span
Trench restoration
Notes: The first group of quality assurance elements belongs to Category A. The elements that are grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.

## Slide 396: Category A
Category A Elements:
1. Cut Back (Pav’t Cutting)
2. Subbase Compaction
3. Cleaning and Tacking
4. Filling
5. Material
6. Compaction
Trench restoration
Notes: The first group of quality assurance elements belongs to Category A. The elements that are grouped into this category are representative of functions deemed most critical to the overall quality and longevity of the finished product. Failure to achieve a “satisfactory” level of performance on any one of these elements will most likely result in the immediate failure of the finished product or contribute directly to its shortened life span.

## Slide 397: Performance Indicators
A. 1. Cutting (Pav’t Cutting) (Ref. RC-30M)
PERFORMANCE INDICATORS
1. Pavement adjacent to original trench excavation not cut back prior to placing bituminous material.
3. Pavement not cut to full depth and/or cuts are less than 1’ from outside edges of original trench excavation and/or adjacent
pavement damaged during excavation.
5. Pavement cut to full depth of pave. Cuts are 1’ or greater from outside edges of original excavation and adjacent pavement not
damaged or disturbed during excavation.
Trench restoration
Notes: 397

## Slide 398: Performance Indicators
A. 2. Subbase Compaction
PERFORMANCE INDICATORS
1. Subbase material not compacted prior to placing bituminous material.
5. Subbase material is properly compacted prior to placing bituminous material.
Trench restoration
Notes: 398

## Slide 399: Performance Indicators
A. 3. Cleaning and Tacking*
PERFORMANCE INDICATORS
1. Vertical faces of adjacent pavement not cleaned or tacked prior to placing bituminous material.
2. Vertical faces of adjacent pavement cleaned but not tacked prior to placing bituminous material.
3. Vertical faces of adjacent pavement tacked but not cleaned or cleaned and tack not uniformly applied prior to placing
bituminous material.
5. Vertical faces of adjacent pavement cleaned and tack applied uniformly to all vertical surfaces of adjacent pavement.
* Use of either compressed air or brooming are acceptable means of cleaning vertical faces of cut pavement. Approved tack coat may be applied with an approved backpack sprayer, kettle or distributor. Brooming or hand brushing are acceptable means of applying tack. Entire surface of vertical faces of pavement cut are to be covered with a uniform film.
Trench restoration
Notes: 399

## Slide 400: Performance Indicators
A.4. Filling**
PERFORMANCE INDICATORS
Material placed in improper lifts or difference in total depth between compacted material placed and the adjacent pavement is more than 2 inches.
3. Material placed in proper lifts. Difference in total depth between compacted material placed and the adjacent pavement is 2 inches or less and material is properly distributed prior to compaction.
5. Material placed in proper lifts. Total compacted depth of material is equal to that of the adjacent pavement, and material is properly
distributed prior to compaction.
** Rake is permissible with 25mm Plant Mix; Lutes are to be used when plant mixed bituminous wearing course material is used. Plant mixed bituminous wearing course material is to be placed in compacted lifts not exceeding 2” in depth for 9.5 mm, 3” for 12.5mm, 4” for 19mm and 5” for 25mm.(Ref. 408, Section 305.3(h) and Pub 242, table 9.5).
Trench restoration
Notes: 400

## Slide 401: Performance Indicators
A.5. Material
PERFORMANCE INDICATORS
1. Unworkable plant mix and/or temperature <230 degrees F.
3. Plant mix bituminous material with reduced workability, hot mix temperature 230 – 250 degrees F.
5. Plant mix bituminous material within temperature specifications and workable.
Trench restoration
Notes: 401

## Slide 402: Performance Indicators
A.6. Compaction
PERFORMANCE INDICATORS
1. No compaction, vehicle wheels used for compaction, or spillage not removed from adjacent surfaces prior to compaction.
3. Compacted, edges not properly pinched. ( Pinch roll toward joint )
5. Properly compacted with vibratory roller or 4-6 ton roller.
Trench restoration
Notes: 402

## Slide 403: Category B
Category B:
Second group of quality assurance elements
The elements that are grouped into this category are representative of functions deemed moderately critical to the overall quality & longevity of the finished product
Marginal performance on a given element in this category, although not desirable, will not in all likelihood directly contribute to the immediate failure or shortened life span of the finished product
Trench restoration
Notes: 403
The second group of quality assurance elements belongs to Category B. The elements that are grouped into this category are representative of functions deemed moderately critical to the overall quality and longevity of the finished product. Unlike Category A, a marginal performance on a given element in this category, although not desirable, will not in all likelihood directly contribute to the immediate failure or shortened life span of the finished product.

## Slide 404: Category B
Category B Elements:
1. Marking
2. Clean-Up
3. Rideability
4. Waste Disposal
(Environmental
Conduct)
Trench restoration

## Slide 405: Performance Indicators
B.1. Marking
PERFORMANCE INDICATORS
1. No marking done prior to sawing or cutting.
3. Pavement marked prior to sawing or cutting on each side of the trench but marks delineating locations to be cut are not straight and/or parallel to each other.
5. Pavement marked prior to sawing or cutting on each side of the trench and marks delineating locations to be cut are straight and parallel to each other.
Trench restoration
Notes: 405

## Slide 406: Performance Indicators
B.2. Clean-Up
PERFORMANCE INDICATORS
Litter and/or debris left on worksite.
5. All project related litter and debris removed from site.
Trench restoration
Notes: 406

## Slide 407: Performance Indicators
B.3. Rideability
PERFORMANCE INDICATORS
Any depression or bump > ½”
3. Depression or bump between ¼” and ½”.
5. No depression or bump > ¼”.
Trench restoration
Notes: 407

## Slide 408: Performance Indicators
B.4. Environmental Conduct (Ref. Pub 113, Activity 711-7121-03)
PERFORMANCE INDICATORS
Project related waste materials ( materials excavated in preparation for patching or trench restoration, or residual bituminous patching material ) improperly disposed of.
5. Project related waste materials ( materials excavated in preparation for patching or trench restoration, or residual bituminous patching material ), is properly disposed of or stockpiled. If disposed of off-site, required property owner release(s) are secured and required due diligence forms are completed.
Trench restoration
Notes: 408

## Slide 409: Operational Sequence Pipe Trench Restoration 711-7121-03
Operational sequence

## Slide 410: Operational Sequence
On Site Process:
A step-by-step procedure which is used for pipe trench restoration projects
Intended to replace the short-term, temporary patch with a long-term, permanent cover.
Detailed direction and guidance for procedures, equipment, and safety
Verifies quality of the finished product
Operational sequence
Notes: 410
In this section we will go step-by-step through the On Site Process, which is used for pipe trench restoration projects.

## Slide 411: Steps 1 and 2
Step 1 – Operators Prepare Equipment:
Equipment operators perform equipment safety inspection including air break check and fill out form 614
Step 2 – Foreman Communications:
Foreman conducts a safety talk, reviews work zone traffic control requirements
Operational sequence
Notes: 411

## Slide 412: Step 3
Step 3 – Foreman sends truck to plant and coordinates delivery time with operator:
When performing trench patching operations during cool/cold weather months or when repairing multiple small patches, using Hot Asphalt Storage units should be considered to minimize wasted materials.
Operational sequence
Notes: 412

## Slide 413: Step 4
Step 4 – Safety Setup:
Work zone set-up is installed using the correct PATA to provide proper traffic control through the work area
This protects both the traveling public and department personnel
Operational sequence
Notes: 413
Next, in step 3, the work zone set-up is installed to provide proper traffic control through the work area, protecting both the traveling Public and department personnel.

## Slide 414: Steps 5 and 6
Step 5 - Ensure all crews members are properly attired per the Safety Policy Manual, Pub 445:
Step 6 - Flaggers are positioned before
crew and equipment move on to the highway.
Operational sequence
Notes: 414

## Slide 415: Step 7
Step 7 – Marking the roadway:
  Minimum 12” from original excavation
  In sound pavement
  Straight line
Operational sequence
Notes: 415

## Slide 416: Step 8
Step 8 – Cut the Pavement:
Cut to sound pavement
Full depth
Vertical edges
Square corners
Operational sequence
Notes: 416

## Slide 417: Step 9
Step 9 – Remove old material:
Operational sequence
Notes: 417
.

## Slide 418: Step 10
Step 10 - Clean Patch Area:
  Vertical face of the cut pavement
  Broom adjacent pavement surface
Operational sequence
Notes: 418

## Slide 419: Step 11
Step 11 – Compact disturbed material:
Operational sequence
Notes: 419

## Slide 420: Step 12
Step 12 – Apply Tack:
Apply evenly to all bituminous surfaces
Allow time for oil to break before adding material
Operational sequence
Notes: 420

## Slide 421: Step 13
Step 13 – Apply New Material:
    Within workable temperatures and no clumps
    Add 1.25 inches of un-compacted material for each inch of material removed
    Place multiple lifts in accordance with Publication 242 when greater than four inches
Operational sequence
Notes: 421

## Slide 422: Step 14
Step 14 – Lute Material:
  Raking is permitted only when using 25MM material
  Do not level with excavator bucket
Operational sequence
Notes: 422

## Slide 423: Step 15
Step 15 – Clean Adjacent Area Before Compacting:
Operational sequence
Notes: 423

## Slide 424: Step 16
Step 16 – Compact New Material:
  Pinch edges
  Compact to no visible movement
  Match existing grade with no depressions or bumps greater than ¼ inch
Operational sequence
Notes: 424

## Slide 425: Step 17
Step 17 – Monitor Operation
  If more than one patch, ensure that the removal operation does not get too far ahead of the filling operation
  Do not open to traffic until material has cooled to 140 degrees
Operational sequence
Notes: 425

## Slide 426: Step 18
Step 18 – Monitor Safety Throughout The Operation:
Monitor the health of the crew, watch for signs of heat related illness
Monitor the Work Zone setup and interaction with adjacent traffic
Monitor the conduct of flaggers
Operational sequence
Notes: 426

## Slide 427: Step 19
Step 19 – Moving from the roadway:
This step is performed when stopping the operation for greater than 15 minutes
  Pull the equipment off of the roadway
  Move flaggers from the roadway
  Turn signs if taking break for greater than 15 minutes or moving to new location
  Reverse the steps for moving back onto
  roadway
Operational sequence
Notes: 427

## Slide 428: Step 20
Step 20– Continue Operations:
Steps 7 through 19
Operational sequence
Notes: 428

## Slide 429: Step 21
Step 21 – Breaking down the operation at the end of the day:
This step is performed at the conclusion of the operation
  Clean the work area
  Pull the equipment off of the roadway
  Move flaggers from the roadway
  Remove WZTC signs
  Return to the assembly area
Operational sequence
Notes: 429

## Slide 430: Step 22
Step 22 – Clean equipment and prepare for next day’s activities:
This step is performed at the assembly or equipment staging area
  Clean equipment and hand tools
  Complete equipment M-614 documents
  Conduct an informal AAR with crew members to discuss the strengths and opportunities observed that day
  Go home safely!
Operational sequence
Notes: 430

## Slide 432: Preventative maintenance
Preventative Maintenance

## Slide 433
Identify actions that, when taken, will help maximize the useful life of the completed maintenance activity.
Preventative Maintenance

## Slide 434: Preventive Maintenance
Perform routine inspections
Perform inspections during and after major weather events
Maintain tail ditches
Preventative Maintenance

## Slide 435: Preventive Maintenance
Clean inlets
Perform flushing activities as needed
Vegetation control
Preventative Maintenance

## Slide 436: Follow-up Activities
Shoulder cutting that includes handwork around inlets
Preventative Maintenance

## Slide 437: Preventive Maintenance
Indentify other factors that could impact the effectiveness of the pipe being replaced
Preventative Maintenance

## Slide 438: Preventive Maintenance
Development of area (legal and illegal driveways, storm water runoff, etc.)
Preventative Maintenance

## Slide 439: Preventive Maintenance
  Shoulder washouts
Preventative Maintenance

## Slide 440
Identify actions that, when taken, will help maximize the useful life of the completed maintenance activity.
Preventative Maintenance

## Slide 441
Identify actions that, when taken, will help maximize the useful life of the completed maintenance activity.
Preventive maintenance activities needed to maintain functioning drainage systems include:
Routine inspection
Maintenance of inlet and tail ditches
Clean inlets
Perform flushing activities as needed
Vegetation control
Shoulder cutting
Development of the adjacent property
Preventative Maintenance

## Slide 443: Operational Sequence
Technical Training

## Slide 444: Operational Sequence
On Site Process:
A step-by-step procedure which is used for all pipe replacement projects
Detailed direction and guidance for procedures, equipment, and safety
Verifies quality of the finished product
Operational sequence
Notes: 444
In this section we will go step-by-step through the On Site Process, which is used for pipe replacement projects.

## Slide 445: Operational Sequence Step 1
Step 1 – Foreman Communications:
Foreman conducts a relevant safety talk
Foreman determines the material needs for the day and tells the operators what each should load and bring to the jobsite
Foreman reviews work zone traffic control requirements
Foreman reviews documents to ensure all required completed forms and permits are available to take to the worksite:
  Pa 1 Call document
  Authorization To Enter (Form 666)
  Permit (if required)
Operational sequence
Notes: 445

## Slide 446: Operational Sequence Step 2
Step 2 – Operators Prepare Equipment:
Equipment operators perform equipment safety inspection +-
including air break check and fill out Form 614
Operational sequence
Notes: 446

## Slide 447: Operational Sequence Step 3
Step 3 – Load Material:
Equipment operators Load material needed to complete the days planned activities
Operational sequence
Notes: 447

## Slide 448: Operational Sequence Step 4
Step 4 – Safety:
Work zone set-up is installed to provide proper traffic control through the work area
This protects both the traveling public and department personnel
Always use the correct PATA for the type of work and conditions encountered
Operational sequence
Notes: 448
Next, in step 4, the work zone set-up is installed to provide proper traffic control through the work area, protecting both the traveling Public and department personnel. Figure PATA 11a of Publication 213 is the most commonly used traffic control set-up. Please note: the use of a pilot vehicle is considered a best practice. If a pilot vehicle is incorporated as part of your work zone traffic control set-up, then a shadow vehicle will not be required.

## Slide 449: Operational Sequence Steps 5 and 6
Step 5 - Ensure all crews members are properly attired per the Safety Policy Manual, Pub. 445
Step 6 - Flaggers are properly positioned as per Pub. 213
Operational sequence
Notes: 449

## Slide 450: Operational Sequence Step 7
Step 7 – Mark and Cut Roadway (This step is required if the roadway was not cut in advance):
Mark and cut the roadway before cutting as outlined in Categories B-8 and C-1 of the Pipe Replacement Quality Assurance Review Form
Operational sequence
Notes: 450

## Slide 451: Operational Sequence Step 8
Step 8 – Establish grade:
Grade shall be established in accordance with Category A-2 of the Pipe Replacement Quality Assurance Review Form
The finished installation must have a minimum of 12 inches of cover material
The finished installation must have a minimum of ¼ inch per foot fall
Operational sequence
Notes: 451

## Slide 452: Operational Sequence Step 8
Step 8 – Establish grade (cont’d):
If using a hand held locke level remember that the maximum effective range is 25 feet in each direction of the level
If using an automatic level remember to set the level up outside of the immediate work area so that it does not interfere with the operation
Operational sequence
Notes: 452

## Slide 453: Operational Sequence Step 8
Step 8 – Establish grade (cont’d):
Once inlet and outlet grades are established, mark the entire length of the installation at 4’ increments. This will help maintain the proper flow line through the project. At ¼ inch per foot fall the grade will drop 1 inch every four feet.
Document elevation at each 4 foot mark for quick accurate references
Operational sequence
Notes: 453

## Slide 454: Operational Sequence Step 9
Step 9 – Identify and remove obstacles:
Cut brush or trees at inlet and outlet
Remove guiderail and signs if present
If brushing or sign and guiderail removal is required, remember to charge assemblies accordingly
Check for utilities
Operational sequence
Notes: 454
.

## Slide 455: Operational Sequence Step 10
Step 10 – Excavate the pipe trench:
To help minimize damage to the adjacent pavement, begin excavation from the center of the trench and work out to the sides of the trench
Operational sequence
Notes: 455

## Slide 456: Operational Sequence Step 10
Step 10 – Excavate the pipe trench:
The finished pipe trench should have vertical walls except in cases where trench stability is questionable or in cases where the depth is greater than 5 feet. In these cases use the formula detailed in Category B-8 of the Pipe Replacement Quality Assurance Review Form.
Operational sequence
Notes: 456

## Slide 457: Operational Sequence Step 10
Step 10 – Excavate the pipe trench (cont’d):
When excavating the trench, the old pipe must be separated from the clean fill as material is excavated from the trench
Operational sequence
Notes: 457

## Slide 458: Operational Sequence Step 10
Step 10 – Excavate the pipe trench (cont’d):
The finish grade of the excavated ditch must be 6 inches greater than the finish grade of the flow line to accommodate the bedding material.
Operational sequence
Notes: 458

## Slide 459: Operational Sequence Step 11
Step 11 - Disposal of excavated material:
Excavated material is loaded onto trucks and hauled to the nearest approved dumpsite
Operational sequence
Notes: 459

## Slide 460: Operational Sequence Step 11
Step 11 - Disposal of excavated material (cont’d):
Excavated material shall only be disposed of at Department owned facilities or on private property where property owners have completed and signed “Authorization To Enter” Forms
Operational sequence
Notes: 460

## Slide 461: Operational Sequence Step 11
Step 11 - Disposal of excavated material (cont’d):
Excavated material shall only be dumped as indicated on the completed Authorization To Enter form
Operational sequence
Notes: 461

## Slide 462: Operational Sequence Step 12
Step 12 – Check trench grade
Operational sequence
Notes: 462

## Slide 463: Operational Sequence Step 13
Step 13 – Place bedding material:
6 inches of aggregate is placed in the trench
  2-A for plastic and corrugated metal pipe
  # 8 for concrete pipe
Operational sequence
Notes: 463

## Slide 464: Operational Sequence Step 13
Step 13 – Place bedding material (cont’d):
When placing concrete elliptical pipe, a cradle equal to 15% of the rise of the pipe is required
Operational sequence
Notes: 464

## Slide 465: Operational Sequence Step 14
Step 14 – Check finished trench grade
Operational sequence
Notes: 465

## Slide 466: Operational Sequence Step 15
Step 15 – Unload pipe and place in the excavated trench:
Care should be taken to ensure the safety of the crew members when handling the pipe
Care should be taken to ensure the pipe is not damaged during this part of the operation
Operational sequence
Notes: 466

## Slide 467: Operational Sequence Step 16
Step 16 – Inspect the pipe for any damage and make necessary repairs
Operational sequence
Notes: 467

## Slide 468: Operational Sequence Step 17
Step 17 – Join the sections of pipe together, plastic pipe:
Plastic Bands Secured with Nylon Draw Straps. Bands are Constructed to Match the Exterior Contour (Valleys and Ridges) of the Pipe Used. Always Wear Gloves.
Operational sequence
Notes: 468

## Slide 469: Operational Sequence Step 17
Step 17 – Join the sections of pipe together, corrugated metal pipe (cont’d):
Metal Bands Secured with Nuts and Bolts. During the Process of Tightening the Bands, Periodic Tapping will be Necessary to Insure a Snug Fit. A Rubber Mallet Should be Used to Avoid Damage to the Galvanized Coating. Always Wear Gloves.
Operational sequence
Notes: 469

## Slide 470: Operational Sequence Step 17
Step 17 – Join the sections of pipe together, concrete pipe (cont’d):
Rolled Pipe Joint Mastic
Pipe Joint Compound (5 Gal. Buckets)
Operational sequence
Notes: 470

## Slide 471: Operational Sequence Step 18
Step 18 – Ensure pipe is properly aligned:
Operational sequence
Very nice pipe alignment both Horizontally and vertically.
Notes: 471

## Slide 472: Operational Sequence Step 19
Step 19 – Backfilling the pipe trench, first lift:
Fill material should be at or near optimum moisture content, material should be damp but not wet
Material should be introduced slowly as to not adversely affect the alignment of the pipe
The first lift of material should be equal to approximately 75% of the height of the pipe to minimize the chances of deflection or lifting of the pipe
Operational sequence
Notes: 472

## Slide 473: Operational Sequence Step 19
Step 19 – Backfilling the pipe trench, flowable fill (cont’d):
Pipe must be held in a stable position of alignment both vertically and horizontally during the introduction of material
Pipe must be elevated from the bottom of the excavation to allow fill material to completely surround the pipe
Pipe trench must be encapsulated to prevent the material from escaping the trench
Compaction/vibrating the material is not required
Operational sequence
Notes: 473

## Slide 474: Operational Sequence Step 20
Step 20 – Compacting backfill:
Compactors Should be Operated in Tandem to Avoid Moving the Pipe out of Horizontal Alignment
Compaction efforts should continue until there is no visible movement in the material
Operational sequence
Notes: 474

## Slide 475: Operational Sequence Step 21
Step 21 – Backfill, subsequent lifts:
  After the initial lift has been compacted additional material should be added in 4” to 6” lifts
  The use of a skid-steer loader is considered a best practice for this step of the operation
  Adding material directly from a dump truck can result in too much material being introduced to the trench requiring additional hand work
Operational sequence
Notes: 475

## Slide 476: Operational Sequence Step 22
Step 22 – Compacting backfill, subsequent lifts:
No compaction directly over the top of the pipe until the depth of backfill over the pipe is 12” or greater
Compaction efforts should continue until there is no visible movement in the material
Operational sequence
Notes: 476

## Slide 477: Operational Sequence Step 23
Step 23 – Backfilling and compaction:
Continue Steps 21 and 22 until the trench has been filled
  Level with the adjacent roadway if not adding a bituminous top
  2” to 3” below the adjacent roadway if adding a bituminous top material
Compaction efforts should continue until there is no visible movement in the material
Operational sequence
Notes: 477

## Slide 478: Operational Sequence Step 24
Step 24 – Adding temporary bituminous material:
This step is not always required, however, it is recommended when the pipe replacement operation takes place on roadways with a high ADT
The bituminous material should be placed and compacted to meet the adjacent roadway
Final trench restoration will eventually replace this bituminous material (See “Trench Restoration”)
Operational sequence
Notes: 478

## Slide 479: Operational Sequence Step 25
Step 25 – Inlet and outlet ditching:
Inlet and outlet ditches should be cleaned in conjunction with the pipe replacement
Ditching performed greater than 15 feet from the end of the pipe should be charged to the appropriate Assembly
Operational sequence
Notes: 479

## Slide 480: Operational Sequence Step 26
Step 26 – Erosion and sedimentation (E&S) controls:
When E&S controls should be installed in accordance with Category B-6 of the Pipe Replacement Quality Assurance Review Form
When E&S controls are used, time should be charged to the appropriate Assembly
Operational sequence
Mulching
Seeding
Notes: 480

## Slide 481: Operational Sequence Step 26
Step 26 – Erosion and sedimentation (E&S) controls (cont.d):
When E&S controls should be installed in accordance with Category B-6 of the Pipe Replacement Quality Assurance Review Form
When E&S controls are used, time should be charged to the appropriate Assembly
Operational sequence
Straw Bales
Silt Fence
Rock Lining
Notes: 481

## Slide 482: Operational Sequence Step 27
Step 27 – Installing end treatments:
Inlets are installed on both inlet and outlet ends of the pipe in accordance with Category B-1 of the Pipe Replacement Quality Assurance Review Form
End treatment installation should be charged to the appropriate Assembly
Operational sequence
Notes: 482

## Slide 483: Operational Sequence Step 28
Step 28 - Monitor health of employees:
Ensure personal protective equipment is being used correctly
Monitor employees for heat exhaustion symptoms during warm weather
Operational sequence
Notes: 483

## Slide 484: Operational Sequence Step 29
Step 29 - Monitor work zone traffic control:
Monitor flagger conduct
Monitor signs
Operational sequence
This is unacceptable flagger behavior!
Notes: 484

## Slide 485: Operational Sequence Step 30
Step 30 - Breaking down the operation at the end of the day:
This step is performed at the conclusion of the operation
  Clean the roadway again, remove all debris
  Delineate the work area if needed
  Move flaggers from the roadway
  Remove WZTC signs
  Return to the assembly area
Operational sequence
Notes: 485

## Slide 486: Operational Sequence Step 31
Step 31 – Properly dispose of used pipe:
Operational sequence
Notes: 486

## Slide 487: Operational Sequence Step 32
Step 32 - Clean equipment and prepare for next day’s activities:
This step is performed at the assembly or equipment staging area
  Clean equipment and hand tools
  Complete equipment M-614 documents
  Conduct an informal AAR with crew members to discuss the strengths and opportunities observed that day
  Go home safely!
Operational sequence
Notes: 487

## Slide 488
This concludes the PennDOT Pipe Replacement Training.
Thank you for participating.
Operational sequence

## Slide 490: Pipe replacement Instructor-Led Section

## Slide 491
THE LEARNING OBJECTIVES FROM THIS PRESENTATION ARE:
Quality Assurance
Pipe Replacement
Proper Work Zone Selection
Proper procedures to insure a properly installed pipe
The Components that make up the pipe QA
The Performance indicators or the scoring of the elements
The Elements within those categories
Safety issues
Innovative ideas
The Categories of the QA
Environmental issues and concerns
Notes: Read objectives

## Slide 492: Pipe Replacement Quality Control Source Documents
  The pipe replacement quality control source documents are:
          Publication 113 – Foreman’s Manual
          Publication 72M – Roadway Construction Standards
          Publication 464 – Maintenance Field Reference for Erosion & Sedimentation Control
          QA review form M-7324 – Pipe Quality Assurance Form
Notes: Information on pipe replacement can be found in these sources.

## Slide 493: Pub 113
Notes:           Publication 113 – Foreman’s Manual

## Slide 494
Publication 72M
Notes:           Publication 72M RC Standards Chapter 30 are detailed drawings of pipe and drainage installation

## Slide 495
          Publication 464
Notes:           Publication 464 – Descriptions of erosion and sedimentation control measures required for various operations and activities.

## Slide 496
Notes: This is the form used to rate and evaluate pipe replacement installation

## Slide 497
Quality Assurance
Work Zone Traffic Control
The quality of the end product of all highway maintenance operations can be directly related to the extent to which we have successfully addressed the issue of maintaining traffic around or through the work area.
Effective work zone traffic control provides an environment that assures the maximum protection for crew members and the motoring public while minimizing delays and confusion.
The process of determining which traffic control PATA is most appropriate for your operation is outlined in the current work zone traffic control Publication ( Pub. 213).
The two work zone traffic control figures most commonly used on pipe replacement operations are:
Provisions for chapter 212 are issued under the PA Vehicle Code making WZTC the Law.
Notes: WZTC is the Law.

## Slide 498
Notes: Both ends of the work zone need to be set up to allow shifting/switching lanes. Ex. Buffer zone, flagger placement, communication with work crew and flaggers. Most common mistakes that are made in the field on pipe operations.

## Slide 499
Quality Assurance
Work Zone Traffic Control
Pipe Replacement
PATA 10a.
Maintaining Thru Traffic With Flaggers
Notes: Very nice 10a work zone setup. Flagger placed on top of hill. Longitudinal cone spacing and condition of cones.

## Slide 500
Quality Assurance
Work Zone Traffic Control
Pipe Replacement
PATA 10a.
Using Steel Plates to Accommodate Thru Traffic
Notes: Plates are not allowed by all districts / counties. When plates are used monitor conditions such as condition of the plate (is it bowing), moving under traffic, soil and road conditions under traffic, workers away from plates when traffic is flowing, delineate plates.

## Slide 501
Quality Assurance
Work Zone Traffic Control
Pipe Replacement
Many crews utilize high strength steel plates to accommodate thru traffic under PATA 10a. Extreme caution must be exercised during placement and removal. Use of steel plates is not common practice in all Districts/Counties. When used consult with County Management.
Notes: Employees need to be cautious when placing the plates. (Swinging and bouncing) Use the proper lifting apparatus and equipment when placing plates.

## Slide 502
Notes: For the safety of the motoring public and the workers, 11d (road closure) is the best PATA to use for pipe replacement. Pre-planning and approval must be conducted.

## Slide 503
Road closed signs need to be placed on the road blocking traffic as they are shown on the left.
A typical detour sign used in a Traffic Control Plan.
Notes: Place signs as they are shown on the traffic control plan. Are the directional panels boards ok?

## Slide 504
Quality Assurance
Pipe Replacement Operations
The quality assurance process identifies those components or elements of an operation required to realize an objective. The objective here…is safe quality pipe replacement.
Each element consists of indicators representing levels of performance in the execution or completion of a given element:
Each element is then grouped into one of three categories:
The Quality Assurance Review
Notes: Read this slide.

## Slide 505
Quality Assurance
Pipe Replacement Operations
Category A: Elements Grouped into this Category are Representative of Functions Deemed Most Critical to the Overall Quality and Longevity of the Finished Product. Failure to Achieve a “Satisfactory” Level of Performance on Any One of These Elements Will Most Likely Result in the Immediate Failure of the Finished Product or Contribute Directly to its Shortened Life Span.
Category B: Elements Grouped into this Category are Representative of Functions Deemed Moderately Critical to the Overall Quality and Longevity of the Finished Product. Unlike Category A, “Marginal” Performance on a Given Element in This Category (Although not Desirable), will in all Likelyhood not Contribute Directly to the Immediate Failure or Shortened Life Span of the Finished product.
Category C: Elements Grouped into this Category are Representative of Functions Deemed Nominally Critical to the Overall Quality and Longevity of the Finished Product. Unlike Category B, “Less than Marginal” Performance on a Given Element (Although not Desirable), Will Not Contribute to the Premature Failure of the Finished Product.
Notes: Explain the Categories focusing on bold underlined words.
Cat. A is most critical to the job,ect.

## Slide 506
A. 1. Flow Line (Ref. Pub 113, Pub 408 Sec. 601)
1. Improper slope.
3. Grade line slightly irregular, with minimum slope of ¼” of fall per foot overall.
5. Uniform slope of ¼” or greater of fall per foot.
Quality Assurance
Pipe Replacement Operations
¼” of Fall/Ft. or > Overall
Vertical Alignment is True
Note that ¼” per foot is the “Minimum” Fall per Foot
Notes: Note that ¼” per foot is the “Minimum”, greater slopes are acceptable to meet field conditions. For concrete pipe the bell end needs to be placed at the upstream end.

## Slide 507
String line used to maintain the proper grade
Notes: Control elevations are set at each end and the string line used to maintain the proper grade and achieve proper bedding depth and maintain correct flow line.

## Slide 508
Bedding placed and leveled off to the proper uniform slope.
Pipe placed in the trench after the bedding has been properly placed.
Notes: Excavating the entire roadway allows for better pipe placement on the bedding and truer alignment. This takes more planning because may involve closing the roadway.

## Slide 509
2. Inlet/Outlet Flow Established
1. Inlet and/or outlet ditches restricted > 30%. 3. Inlet and/or outlet ditches partially restricted <30%. 5. Inlet and outlet ditches open with no restrictions.
Quality Assurance
Pipe Replacement Operations
Outlet ditch completely blocked. additional ditch cleaning required.
Inlet partially restricted.
Unless stabilized, continued sediment migration will eventually choke the flow and block the pipe
Notes: Some ditching might be required to allow water to enter or exit the pipe.

## Slide 510
A. 2. Inlet/Outlet Flow Established (cont’d.)
Quality Assurance
Pipe Replacement Operations
Section 417 of the Highway Law of 1945 “Drains and Ditches”: The Department shall have the authority to enter upon any lands and cut, open, maintain and repair such drains or ditches, inlets or outlets as are necessary to carry the waters from roads and highways.
Outlet ditch cleaning how far can you go?
If any person shall stop or fill up any such drain or ditch, or shall divert or change the course thereof without authority from the Department, such person shall upon summary conviction thereof, for every such offense pay a fine together with costs of prosecution.
The question is…..How far do you “Need” to go?
Notes: Good customer service is to contact the property owner even if within the right of way.

## Slide 511
Quality Assurance
Pipe Replacement Operations
Tail ditching being completed to allow the water to flow away from the pipe without restriction.
Notes: Do not forget to use pub 464 to determine the proper E & S controls required.

## Slide 512
Quality Assurance
Pipe Replacement Operations
Approved backfill material is 2A aggregate
Material should most desirably be at or near its’ optimum moisture content value….(it should be damp but with no water running from it).
Field test by compressing in hands in the shape of a ball. If material retains shape when hands are opened, the material is suitable for use.
A. 3. Backfill * (Ref. Pub 113, Pub 408 Sec. 601)
1. Using existing excavated or improper material; or placing backfill in loose lifts exceeding 8” in depth prior to compaction.
3. Proper material placed in loose lifts of 4” to 8” in depth prior to compaction.
5. Proper material placed in loose lifts no greater than 4” in depth prior to compaction or 8” loose lifts compacted with a vibratory roller.
Notes: Material that is to wet or to dry will not compact properly. Water can be added to dry material to obtain desired moisture content. Approved backfill material is 2A aggregate

## Slide 513
Material is too dry to obtain proper compaction.
Material is too wet to obtain proper compaction.
Notes: When you have dust rising or mud flying the material does not have the proper moisture content.

## Slide 514
Quality Assurance
Pipe Replacement Operations
Material introduced to the trench via backhoe
Material introduced to the trench via skid steer
Skid steer loaders are very versatile, require a much smaller work platform than the backhoe and afford the crew an opportunity to continue with excavation while introducing backfill.
Production is increased and efficiency enhanced thru the use of skid steers….especially in those situations where traffic is detoured and the roadway closed to thru traffic.
Notes: Utilization of the Skid Steer loaders on Pipe Replacement Operations has been Identified as a “Best Practice” and Rightfully so.

## Slide 515
The first lift of back fill is placed to a depth of ¾ of the outside diameter of the pipe and compacted. This is done with plastic and metal pipe to keep the pipe from lifting or deflecting as the material is compacted. Two upright compactors are needed to accomplish this.
Continue back filling the trench with loose lifts of material of up to 4” in depth to the top of the trench. Thoroughly compacting each lift.
Notes: When installing concrete pipe all lifts should be 4” to 8” lifts.

## Slide 516
Temporary bulk heads will need to be installed when the pipe replacement is performed in half widths. This is needed to allow the sections of pipe to be joined together properly with bands.
Bulk heads may be constructed with plywood, used signs or other available materials. The bulk heads must be removed after the pipes are connected.
Notes: Care must be used to ensure the proper pipe alignment is maintained from one side to the other.

## Slide 517
Quality Assurance
Pipe Replacement Operations
Use of Flowable Fill
Ready-mixed flowable fill is commonly a blend of cement, fly ash, sand, and water. Typically it is designed as a low strength, flowable material requiring no subsequent vibration or tamping to achieve 100% consolidation.
Requirements when used as bedding/backfill in pipe replacement operations:
* Pipe must be held in a stable position of alignment both vertically and horizontally during the introduction of material
* Pipe must be elevated from the bottom of the excavation to allow fill material to completely surround the pipe.
* Pipe trench must be encapsulated to prevent the material from escaping the trench.
Notes: Pinning the pipe is required to prevent the pipe from floating while introducing the flowable fill. This an option when you encounter under ground utilities.

## Slide 518
Quality Assurance
Pipe Replacement Operations
Use of Flowable Fill (cont’d.)
Some benefits of using flowable fill in pipe replacement:
* Less excavation time…reduction in trench width.
* Fewer personnel & less equipment… no compaction required
6
6
1’ Greater than Outside Dim.Of Pipe
Notes: Diagram for pinning, elevating and containing the pipe using flowable fill.

## Slide 519
4. Compaction * (Ref. Pub 113, RC-30, Pub 408 Sec. 601) 1. No compaction or compaction effort terminated while extensive backfill movement remains beneath compaction device(s). 3. One upright compactor used, backfill material moist and compaction effort extended till little or no evidence of backfill movement remained beneath the compaction device. 5. Two upright compactors or vibratory roller used, backfill material moist and compaction effort extended till little or no evidence of backfill movement remained beneath the compaction device and compaction devices were not used directly over the centerline of the pipe until the depth of fill reached 12”.
Quality Assurance
Pipe Replacement Operations
* Refer to RC-30 for backfill requirements. [8” lifts with vibratory roller acceptable –“score as 5”] (Pub 408 – sec 601.f).
Double Drum Vibratory Walk-Behind
Single Drum Vibratory Walk-Behind
Upright Compactors
Notes: Hydraulic compactors are NOT to be used. Drum compactors can only be used after there is one foot of cover over the pipe.

## Slide 520
Quality Assurance
Pipe Replacement Operations
PUB 408/2011
(Initial Edition, effective April 1, 2011
SECTION 600 INCIDENTAL CONSTRUCTION 601
(f) Backfilling Trench. After the pipe is laid, backfill the trench as shown on the Standard Drawings. Place material in 100 mm (4-inch) layers. However, 200 mm (8-inch) layers will be permitted if vibratory compaction equipment is used. Compact each layer of backfill to the density shown on the Standard Drawings to a height of 1.2 m (4 feet) above the top of the pipe, for the full trench width. Use mechanical tampers or other acceptable compaction equipment that will not damage the pipe. Do not use excavator-mounted hydraulic plate compactors. Compact backfill material to the density shown on the Standard Drawing as determined by Standard Proctor Density (SPD). Test as specified in Section 206.3(b)1. Test the coarse aggregate backfill for reinforced concrete pipe before placing remaining backfill. If flowable backfill material is used, backfill the trench as shown in the Flowable Backfill Detail on the Standard Drawings, and as specified in Section 220.3.
Notes: (No need to read entire slide) emphasize : Do not use excavator-mounted hydraulic plate compactors. Hydraulic plate compactors can damage the pipe by applying too much down force.

## Slide 521
Quality Assurance
Pipe Replacement Operations
Initial compaction effort
Backfill depth less than 12” over pipe.
Backfill depth 12” and greater over pipe.
Compactors should be operated in tandem to avoid moving the pipe out of horizontal alignment.
No compaction directly over the top of the pipe until the depth of backfill over the pipe is 12” and greater.
Compaction effort directed over the full width of the trench after depth of backfill is 12” and greater over the top of the pipe.
Notes: Correct compaction is the key to quality pipe replacement.

## Slide 522
Quality Assurance
Pipe Replacement Operations
The compaction effort is complete when there is little or no evidence of movement of the backfill material beneath the compaction device(s).
Satisfactory Compaction
.
Notes: Compaction is complete when there is no compactor foot print visible.

## Slide 523
The crew levels off the backfill material to create a uniform lift.
The first lift of backfill should be placed to just above the spring line of the plastic pipe.
Notes: First lift can not cover the pipe because proper compaction will not be achieved on the sides of the pipe.

## Slide 524
Compactors should be used in tandem.
Notes: Compactors used side-by-side until the pipe is covered.

## Slide 525
Each lift of backfill needs to be marked separately. Marking the lifts ahead of time will increase the depth of the following lifts after compaction.
Notes: If you are using 4” lifts , the next lift will be 6” after 2” of compaction. Use of a vibratory drum roller is a best practice if used after one foot of cover is achieved. Mark next lift after each lift is compacted. (Safety discussion top left photo excavated metal pipe should not be standing upright.)

## Slide 526
5. PA 1-Call (Ref PA-1 CALL)
1. No PA 1-Call not made as prescribed by law or excavation begun prior to three working days after placing the PA 1-Call. 3. PA 1-Call made but excavation begun outside the prescribed time frame. (Ten working days beyond notification date ). 5. PA 1-Call made as prescribed by law, work conducted within the prescribed time frame and related PA 1-Call documentation on site ( copy of notification form w/registration # or documentation with notification date & registration # ).
Quality Assurance
Pipe Replacement Operations
You would want to know this gas line is there “BEFORE” you began to excavate.
Know the Law!
Notes: Foreman is responsible for all one call notifications prior to excavation.

## Slide 527
Quality Assurance
Pipe Replacement Operations
Who should make the call?
All contractors, including sub-contractors, must make their own notifications.
The Departments responsibilities
To provide the one call system with specific information to identify the site so that facility owners are able to provide indications of their lines.
A contractor shall use the color “WHITE” to mark a proposed excavation site when exact site information cannot be provided. This includes the shoulder and tail ditch as well as the roadway.
Notification shall be not less than three nor more than ten working days in advance of beginning excavation or demolition work.
Site: The specific place where excavation or demolition work is planned to be performed.
Working Day: A working day means any day except a Saturday and Sunday or a Legal Holiday prescribed by the act of the General Assembly.
Definitions
Notes: Ultimately the foreman is responsible for ensuring the one-call is made and that a copy is available on site

## Slide 528
Disruption of any one of these services can adversely impact day to day life, and unexpectedly finding any one of these during an excavation operation can be very costly, both in terms of human life and dollars.
Quality Assurance
Pipe Replacement Operations
Notes: Review the colors and what they represent.

## Slide 529
Sample of a typical one call response
Notes: This document is required to be on site.

## Slide 530
Items of importance on the notification are:
The “lawful start date”
Responding utilities replies: (i.e. clear, did not respond or area marked).
Notes: Pay attention to local utilities. They may need to be contacted personally if they do not respond.

## Slide 531
Do you still think that making the call is not important?
Notes: So is making the required one call important?

## Slide 532
This bear didn’t make the call!
Notes: If it was powerful enough to kill this bear what will it do to you? The bear bit the cable and the dust.

## Slide 533
Disruption of fiber optic cables can be very expensive!
Areas where utilities are marked should be hand dug.
Notes: Look at how many wires are bundled together. Areas around utilities should be hand dug.

## Slide 534
You would want to know this cable was there before you dig.
Notes: Hand digging could have averted this disruption of service and the expense. This example the wire was only buried 8”.

## Slide 535
6. Location/Length 1. Pipe including any inlet, endwall or end section does not meet the alignment and grade line and does not meet the slope / flowline intercept. 3. Pipe including any inlet, endwall or end section meets the alignment and grade line of the watercourse but does not extend beyond the slope / flowline intercept. 5. Pipe including any inlet, endwall or end section meets the alignment and grade line of the watercourse and extends beyond the slope / flowline intercept for a distance of 1’ or a distance sufficient to insure or improve the stability of the slope.
Quality Assurance
Pipe Replacement Operations
Notes: Changing the pipe location requires a permit from DEP.

## Slide 536
Vertical Alignment Problems
When lowering the elevation of the outlet is not practical, every effort should be made to stabilize that area of the slope receiving water.
This pipe was replaced at the same elevation as the original pipe. The inlet end is under less than 12” of cover. By lowering the inlet end of the pipe & extending the pipe you could have stopped the ongoing erosion of this slope.
Notes: Pre-job surveys will identify these opportunities.

## Slide 537
Notes: When performing inlet/outlet cleaning operations, do not create holes at the outlet end of the pipe.

## Slide 538
A. 7. Trench Width ** (Ref. Pub 113, RC-30, Pub 408 Sec. 601)
1. Too narrow. Insufficient width to allow for compaction equipment on both sides of the pipe for the entire length of the installation. 3. Too wide. Greater than 4’ wider than the outside diameter of the pipe. 5. Sufficient width. Width from 2’ to 4’ greater than the outside diameter of the pipe.
Quality Assurance
Pipe Replacement Operations
** Width is measured from band or bell to trench wall. Additional width permitted for safety to protect workers. Additional width is also acceptable as a means of accommodating water along one side of the trench during installation.
Insufficient trench width results in insufficient compaction.
It can also result in damage to the pipe. The operator attempted to force the compactor by the bell of the pipe and in doing so, the pipe was damaged.
Width of this tamper foot was 10”.
Sufficient trench width is determined by measuring here.
Notes: This trench is not wide enough to accommodate the compactor or the pipe is skewed in the trench.

## Slide 539
Quality Assurance
Pipe Replacement Operations
10”
10”
12”
Maximum performance when operated in a vertical position.
Trench too narrow to allow compactor to be operated in a vertical position.
Impact value is maximized and energy properly directed when operated in vertical position.
10”
14”
90
26”

## Slide 540
Quality Assurance
Pipe Replacement Operations
10”
10”
12”
10”
14”
90
26”
Maximum performance when operated in a vertical position.
Trench too narrow to allow compactor to be operated in a vertical position.
Impact value is decreased and energy is misdirected.
Notes: Run through the animation and explain the loss of compaction due to the compactor not being vertical.

## Slide 541
Nice vertical sides
Notes: Sides are vertical allowing for proper compaction around sides of pipe

## Slide 542
Excavator bucket deflection resulting from resistance.
x
Y
Quality Assurance
Pipe Replacement Operations
Horizontal deflection during excavation
Width of cut on surface
Trench width at planned elevation of installation.(midpoint of pipe)
This type of horizontal deflection is a common occurrence during excavation. Is it a problem?
It can be… If your trench width calculations simply included the greatest outside dimension of the pipe and to it you added 2’ (1’ on each side of the pipe), and failed to recognize the deflection that routinely occurs, you will have insufficient width at the point of installation (Midpoint of the pipe), as illustrated above.
Notes: This shows where to correctly measure the width of the trench.

## Slide 543
Quality Assurance
Pipe Replacement Operations
As a rule, horizontal deflection cannot be eliminated during excavation, but it is possible to minimize it If:
Horizontal deflection during excavation
Remove bituminous wearing and base course.
Begin excavation against trench wall.
Continue excavation against adjacent trench wall.
Excavate material from center of trench. Repeat sequence (2. thru 4.)
( 1. )
( 2. )
( 3. )
( 4. )
You’re using a backhoe to do the excavation
The width of the trench on surface is 60” or greater
Beginning excavation in the center of the trench increases the extent to which horizontal deflection will occur along the trench wall
Lateral Resistance
Lateral Resistance
No Lateral Resistance
Notes: This is the text-book method of excavating the trench.

## Slide 544
Quality Assurance
Pipe Replacement Operations
It won’t fit……
Trench width was adequate
If the first section is incorrectly positioned and backfilled, the entire installation will be skewed
Very likely that this will be the end result. here, no compaction will be possible for a distance of approximately 8’ on one side of the pipe.
What happened?
Notes: Pipe was not placed in the center of the trench. Be Certain Alignment is True “Before” Placement and Backfilling Begins

## Slide 545
It is very important that you remove the entire existing pipe
Notes: Make cut width wide enough to remove entire existing pipe. Take care when marking both ends of pipe for cut lines

## Slide 546
Quality Assurance
Pipe replacement operations
Considerations in determining trench width:
Greatest outside diameter of pipe to be installed.
Depth of the excavation, specifically to the midpoint or spring line of the pipe being installed.
Nature of the soil to be excavated.
Length of the Excavation.

## Slide 547
1. End Treatment (Ref. Pub 113, Pub 23 Ch 8, RC-33 & 34, Pub 408 Sec. 605)
1. Not properly aligned (parallel), with edge of roadway, no end treatment applied, or establish width of the shoulder restricted by placement too close to edge of pave. 3. Stone headwall only. 4. Stone headwall and endwall. 5. Concrete, masonry or treated timber headwall; gabion basket; drop inlet or flared end section Installed or scheduled and properly aligned (parallel) with edge of roadway and established shoulder width not restricted.
Quality Assurance
Pipe Replacement Operations
Notes: Headwalls must be placed parallel to the road, not perpendicular to the pipe. This is a safety issue to the motoring public when improperly installed.

## Slide 548
.
Quality Assurance
Pipe Replacement Operations
SHOULDER
Encroachment into the established shoulder area most frequently occurs when constructing or installing end walls or headwalls on drainage systems that run diagonally to the centerline of the roadway.
Notes: By placing the headwalls Perpendicular to the pipe you will loose shoulder area

## Slide 549
Quality Assurance
Pipe Replacement Operations
Some standard and not so standard approaches
Formed in place and pre-cast drop inlets
Loosely placed field and mountain stone
Plastic end walls

## Slide 550
Quality Assurance
Pipe Replacement Operations
Some standard and not so standard approaches
Pinned concrete bags
Stacked 90lb. bags of Quikrete
Cinder block

## Slide 551
Field stone is used to form the headwall
Field stone is placed as the pipe is backfilled locking the stone into the backfill
Notes: Installing the stone headwall as you are backfilling will lock the stone together

## Slide 552
A precast headwall is used.
When using precast headwalls or inlets you must consider the skew of the pipe.
Notes: Headwall were constructed during dark hours of winter operations (shift work)

## Slide 553
100+ slides have been removed to save file space…